## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Chhoemkanun (village code 314579) under Ramnagar Doemkanun Ground water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000750/2021-2022 | 2208/BD-I | 10/12/2021 | 09/04/2022 | AQUATHERM WATER TREATMENT PRIVATE LIMITED | 89.24 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.10.2021 to 31.12.2021 | Assistant Engineer | Junior Engineer-II | ORD/000826/2021-2022 | 1780/BD-I | 30/09/2021 | 31/12/2021 | AVINABA ENGINEERING CONCERN | 0.45 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.10.2021 to 31.12.2021. | Assistant Engineer | Junior Engineer-II | ORD/000825/2021-2022 | 1779/BD-I | 30/09/2021 | 31/12/2021 | AVINABA ENGINEERING CONCERN | 0.45 | 0 | 0 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer,Assistant Engineer-II | JE,Junior Engineer-II | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 27/12/2022 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 0 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-57C/5576 Bolero Diesel car for official use of Assistant Engineer-II, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000872/2021-2022 | 2280/BD-I | 27/12/2021 | 27/12/2022 | SEBAYAN CONSTRUCTION | 1.81 | 0 | 0 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000009/2021-2022 | 140/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 15.4 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000870/2021-2022 | 2279/BD-I | 27/12/2021 | 27/12/2022 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 0 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000219/2020-2021 | 983/BD-I | 17/12/2020 | 15/02/2021 | AZAD ENTERPRISE | 11.16 | 0 | 0 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/6299 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer, Raghunathganj Sub Division, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000455/2020-2021 | 443/BD-I | 30/03/2021 | 30/09/2021 | AVINABA ENGINEERING CONCERN | 0.91 | 0 | 0 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kazipara (Village code 314608) under Kazipara Water Supply Scheme of Jalangi Block and village of Ramnagar Doemkanun (Village code 314578) under Ramnagar Doemkanun Water Supply Scheme of Raninagar-II Block of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000838/2021-2022 | 49/BD-I | 27/01/2022 | 26/07/2022 | M/S S.DAS & ENTERPRISE | 337.04 | 0 | 0 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Hiring of one no. Car No- W.B-57E/2525 Scorpio Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer | Junior Engineer-II | ORD/000869/2021-2022 | 2278/BD-I | 27/12/2021 | 27/12/2022 | M/S SAJAHAN CHOWDHURY | 1.81 | 0 | 0 | 1
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under RAMNAGAR DOEMKANUN ,KOMNAGAR and BANSGARA ZONE-II ground Water based Water Supply Scheme under Raninagar-II Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000109/2023-2024 | 438/BD-I | 12/07/2023 | 03/06/2025 | MAA CONSTRUCTION | 93.76 | 0 | 0 | 30
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Egrarashi (Village code 314576) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000218/2020-2021 | 982/BD-I | 17/12/2020 | 15/02/2021 | MAA CONSTRUCTION | 5.73 | 0 | 0 | 1
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Laying of new pipeline for Providing Balanced Functional Household Tap Connection (FHTC) which is not covered by existing distribution pipeline from nearest Ground water supply scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanun Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer |  | ORD/000380/2021-2022 | 1464/BD-I | 16/08/2021 | 31/08/2021 | SANTANU BISWAS | 8.61 | 0 | 0 | 0
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Continuation Work Order for Hiring of one no. Car No. W.B-51B/5774 Mahindra & Mahindra make Bolero Diesel car for Assistant Engineer-II, Berhampore Division-I, PHE Dte. for the period from 01.04.2021 to 30.09.2021 | Assistant Engineer | Junior Engineer-II | ORD/000456/2020-2021 | 444/ BD-I | 30/03/2021 | 30/09/2021 | AVINABA ENGINEERING CONCERN | 0.91 | 0 | 0 | 1
16 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Laying of new pipeline for providing Balanced Functional Household Tap Connection (FHTC) which is not covered by exisitng distribution pipeline from nearest Ground Water Supply Scheme in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khastaluk (Village code 314575) under Ramnagar Doemkanun Ground Water Supply Scheme in Murshidabad District under Berhampore Division - I, PHE Dte. (Block-Raninagar-II) | Assistant Engineer | Junior Engineer-II | ORD/000413/2021-2022 | 1442/BD-I | 11/08/2021 | 21/08/2021 | AZAD ENTERPRISE | 4.61 | 0 | 0 | 1
17 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnagar Doemkanun Ground Water Supply Scheme Under Raninagar-II Block In Murshidabad District Under Berhampor | SM/08900 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar Khastaluk (Village code 314586) under Ramnagar Doemkanum Ground Water based Water Supply Scheme for Raninagar-II Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000220/2020-2021 | 984/BD-I | 17/12/2020 | 17/03/2021 | M/S SINHA & SONS | 39.31 | 8.16 | 20.75 | 1
Total | [13 empty] | 614.83 | 8.16 | 1.33