## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08903 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 315524) under Bali Zone-II Ground Water Supply Scheme in Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-II | JE | ORD/000555/2021-2022 | 1886/BD-I | 07/10/2021 | 05/04/2022 | SANJAY BISWAS | 248.74 | 133.42 | 53.64 | 85
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bali Zone-II Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08903 | Retrofitting | Formal work order for Water Supply arrangement for arsenic affected habitation with SOLAR Power connection by Construction/ installation of Community Purification Plant (CPP) unit including Tubewell (125 x50 mm dia ) with DTH (for Population 351-500 & Raw Water As concentration upto 0.15 ppm) at Different habitations [For-9 nos Unit] in different Villages of Block of Farakka ( 9 Units) under Berhampore Division-I , P.H.E. Dte. in the District of Murshidabad. (Site list S/L No 04) | Assistant Engineer,Assistant Engineer-II | JE,Junior Engineer-I | ORD/000563/2021-2022 | 1917/BD-I | 08/10/2021 | 22/12/2021 | MODERN CONSTRUCTION | 143.25 | 89.49 | 62.47 | 80
Total | [13 empty] | 391.99 | 222.92 | 56.87