## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bishnupur (Village code 314780) under Bishnupur Ground Water Supply Scheme of Raninagar I Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-16) | Assistant Engineer | Junior Engineer-II | ORD/000451/2021-2022 | 1884/BD-I | 07/10/2021 | 05/04/2022 | M/S NAYLA CONSTRUCTION | 98.17 | 83.62 | 85.18 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000014/2021-2022 | 141/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 5.82 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Pratappur (village code 314757) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000240/2021-2022 | 1850/BD-I | 07/10/2021 | 15/01/2022 | SRIJON ENTERPRISE | 96.18 | 43.74 | 45.48 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bishnupur Ground Water Supply Scheme Under Raninagar-I Block In Murshidabad District Under Berhampore Division | SM/08904 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kamalpur (village code 314778) under Bishnupur Ground Water based Water Supply Scheme in Raninagar-I Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000241/2021-2022 | 1851/BD-I | 07/10/2021 | 15/01/2022 | SRIJON ENTERPRISE | 96.73 | 30.24 | 31.26 | 1
Total | [13 empty] | 296.9 | 157.6 | 53.08