## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Additional Laying works at village Kedarchandpur, Bundai Nagar and Alampur (Village code-315518,315530, and 315519) to facilitate Functional Household Tap Connection (FHTC) works in connection to Jal Jeevan Mission & Jal Swapna under Ramnachandpur Ground water based Water supply scheme (Nawda,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad . | Assistant Engineer-II | JE | ORD/000793/2021-2022 | 2309/BD-I | 29/12/2021 | 29/03/2022 | SRIJON ENTERPRISE | 43.88 | 35.92 | 81.86 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub-Division, PHE Dte. period for 01.01.2022 to 31.12.2022. | Assistant Engineer,Assistant Engineer-II | JE,Junior Engineer-II | ORD/000871/2021-2022 | 2281/BD-I | 27/12/2021 | 27/12/2022 | TARUN KUMAR BHATTACHARYA | 1.81 | 1.58 | 87.1 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000010/2021-2022 | 144/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 16.44 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kedarchandpur (village code 315518) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000244/2021-2022 | 1854/BD-I | 07/10/2021 | 15/01/2022 | SRIJON ENTERPRISE | 98.62 | 63.5 | 64.38 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bundai Nagar (village code 315530) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000242/2021-2022 | 1852/BD-I | 07/10/2021 | 15/01/2022 | SRIJON ENTERPRISE | 96.17 | 68.46 | 71.18 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnachandpur (Village code 315520) under Ramnachandpur Water Supply Scheme of Nawda Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-14) | Assistant Engineer-II | JE | ORD/000580/2021-2022 | 1924/BD-I | 08/10/2021 | 06/04/2022 | M/S GUHA AND ROY ENTERPRISE | 217.79 | 123.15 | 56.54 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.06.2022 to 31.12.2022. | Assistant Engineer-II | JE | ORD/000014/2022-2023 | 628/BD-I | 30/05/2022 | 30/12/2022 | SOUVIK HALDER | 1.06 | 2.56 | 241.43 | 1
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Laying of Extension and parallel pipeline at Ramnachandpur village due to smooth Functioning of Functional Hosehold Tap Connection at Ramnachandpur zone-I ground Water based water Supply Scheme Under Berhampore Division-I,P.H.E Dte. | Assistant Engineer-II | JE | ORD/000008/2022-2023 | 551/BD-I | 13/05/2022 | 27/06/2022 | ULTRA CONSTRUCTION | 40.55 | 29.76 | 73.4 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ramnachadpur Ground Water Supply Scheme Under Nawda Block In Murshidabad District Under Berhampore Division-I, | SM/08905 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Alampur (village code 315519) under Ramnachandpur Ground Water based Water Supply Scheme in Nawda Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer,Assistant Engineer-II | JE,Junior Engineer-II | ORD/000243/2021-2022 | 1853/BD-I | 07/10/2021 | 05/01/2022 | SRIJON ENTERPRISE | 88.19 | 65.18 | 73.91 | 1
Total | [13 empty] | 604.52 | 390.1 | 64.53