## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08906 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mahespur, Ratnagopbati, Sujapur, Radhaballabhpur, Banamalipur, Harinarayanpur, Sibpur, Srikrishnapur, Arazi Giridharpur, Dayanagar, Arazi Jalalpur, Jhunka and Jalalpur under DAYANAGAR (ZONE-E) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-II |  | ORD/000282/2023-2024 | 979/BD-I | 18/10/2023 | 15/04/2024 | M/S. SUKUMAR SINHA | 402.21 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Dayanagar (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block | SM/08906 | Retrofitting | Laying of 150 mm dia (K-9), 200 mm,250 mm & 300 mm dia DI (K-7) pipeline with interconnection in between Rising Main and Distribution System and 200 mm dia UPVC pipeline of unlead portion within command area of Dayanagar (Zone-E) W/S scheme of Arsenic affected area of Beldanga uncovered W/S scheme under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000244/2023-2024 | 954/BD-I | 13/10/2023 | 12/11/2023 | JAMIRUL CONSTRUCTION | 33.95 | 5.88 | 17.33 | 10
Total | [13 empty] | 436.16 | 5.88 | 1.35