## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Mohula (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Block In | SM/08907 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) laying pipeline in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Halalpur, Mohula, Binkar, Mahishasthali, Gopinathpur & Bhabta under Mohula (ZONE-A) Water Supply Scheme in the district Murshidabad under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000075/2022-2023 | 1641/BD-I | 09/03/2023 | 05/09/2023 | M/S JAN MAHAMMAD | 558.19 | 0 | 0 | 0
Total | [13 empty] | 558.19 | 0 | 0