## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | SM/08908 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000007/2021-2022 | 139/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 28.46 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Chaitanyapur (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Beldanga-I Blo | SM/08908 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Naoda, Sahapur, Ratanpur, Betberia, Kheali, Palaighata, Jafrabad, Sattarpur, Chaitanyapur & Bhadur (Village code 315568, 315569, 315570, 315571, 315572, 315574, 315575, 315576, 315577 & 315579) under Chaitanyapur (Zone-C) Water Supply Scheme of Beldanga -I Block in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000848/2021-2022 | 104/BD-I | 01/02/2022 | 31/07/2022 | M/S JAN MAHAMMAD | 318.48 | 0 | 0 | 1
Total | [13 empty] | 346.94 | 0 | 0