## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bahadurpur (Village code 314894) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I |  | ORD/000456/2021-2022 | 1860/BD-I | 07/10/2021 | 05/01/2022 | M/S. SUKUMAR SINHA | 21.72 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Jayenpur (Village code 314900) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000461/2021-2022 | 1865/BD-I | 07/10/2021 | 05/01/2022 | AJAY MONDAL | 26.81 | 19.86 | 74.08 | 74
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bilkandi (Village code 314904) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000477/2021-2022 | 1879/BD-I | 07/10/2021 | 05/01/2022 | SANJAY BISWAS | 33.81 | 24.37 | 72.09 | 90
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Goljarbag (Village code 314893) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I |  | ORD/000457/2021-2022 | 1861/BD-I | 07/10/2021 | 05/01/2022 | M/S. SUKUMAR SINHA | 42.48 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Begampur (Village code 314908) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000552/2021-2022 | 1910/BD-I | 08/10/2021 | 07/11/2021 | PRADIP KUMAR SAHA | 2.61 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chandipur(Village code 314903) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000755/2021-2022 | 2210/BD-I | 10/12/2021 | 09/01/2022 | ASHIS KUMAR BHATTACHARYYA | 24.26 | 22.55 | 92.94 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ambarnagar (Village code 314905) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000476/2021-2022 | 1878/BD-I | 07/10/2021 | 05/01/2022 | DOBAY CONSTRUCTION | 24.01 | 19.7 | 82.04 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaipara (Village code 314896) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000754/2021-2022 | 2209/BD-I | 10/12/2021 | 30/12/2021 | PRATIMA CONSTRUCTION | 5.21 | 5 | 96.01 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Bhrigurambati (Village code 314892) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000458/2021-2022 | 1862/BD-I | 07/10/2021 | 06/12/2021 | AZAD ENTERPRISE | 12.67 | 11.77 | 92.95 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Raichandpur (Village code 314902) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000478/2021-2022 | 1880/BD-I | 07/10/2021 | 05/01/2022 | DOBAY CONSTRUCTION | 21.62 | 18.26 | 84.45 | 1
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dakshin Ganespur (Village code 314938) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000472/2021-2022 | 1874/BD-I | 07/10/2021 | 05/01/2022 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 21.49 | 18.74 | 87.2 | 1
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bagdhar (Village code 314906) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000475/2021-2022 | 1877/BD-I | 07/10/2021 | 06/12/2021 | MAA SANKARI ENTERPRISE | 20.03 | 17.93 | 89.54 | 1
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Gujasti Rampur (Village code 314898) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000460/2021-2022 | 1864/BD-I | 07/10/2021 | 06/12/2021 | N.H ENTERPRISE | 13.74 | 11.84 | 86.16 | 1
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramnagar (Village code 314909) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000474/2021-2022 | 1876/BD-I | 07/10/2021 | 06/12/2021 | GOUTAM KUMAR CHAUDHURI | 6.69 | 6.11 | 91.3 | 1
16 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Payasti Katiganga (Village code 314891) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000553/2021-2022 | 1911/BD-I | 08/10/2021 | 07/11/2021 | PRAVAT KUMAR GHOSH | 2.97 | 2.27 | 76.41 | 1
17 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Amaipara (Village code 314910) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad -Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000473/2021-2022 | 1875/BD-I | 07/10/2021 | 05/01/2022 | AJAY MONDAL | 27.02 | 20.95 | 77.52 | 1
18 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Amaipara Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000757/2021-2022 | 2223/BD-I | 15/12/2021 | 15/03/2022 | SOM CONSTRUCTION AGENCY | 83.92 | 83.05 | 98.96 | 1
19 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Tantipara (Village code 314895) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000455/2021-2022 | 1859/BD-I | 07/10/2021 | 06/12/2021 | BIJOY SINGHA | 9.03 | 6.19 | 68.47 | 1
20 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kanchannagar (Village code 314907) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000554/2021-2022 | 1912/BD-I | 08/10/2021 | 07/11/2021 | ANKITA ENTERPRISE | 3.35 | 2.8 | 83.5 | 1
21 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofittng Functional Household Tap Connection (FHTC) in connection with JalJeevan Mission and JalSwapna under command area of village of Uttar Ganeshpur (Village code 314890) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I |  | ORD/000459/2021-2022 | 1863/BD-I | 07/10/2021 | 06/12/2021 | DOBAY CONSTRUCTION | 18.6 | 16.1 | 86.53 | 100
22 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sadek Sarai (Village code 314897) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000752/2021-2022 | 118/BD-I | 03/02/2022 | 05/03/2022 | ANKUSH CONSTRUCTION & CO. | 11.58 | 8.85 | 76.44 | 1
23 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.07.2023. | Assistant Engineer-I | JE | ORD/000172/2022-2023 | 1387/BD-I | 23/12/2022 | 23/07/2023 | SOUVIK HALDER | 1.06 | 2.47 | 233.35 | 70
24 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/6299 Bolero Diesel car for official use of Assistant Engineer, Raghunathganj Sub Division, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer |  | ORD/000184/2022-2023 | 1388/BD-I | 23/12/2022 | 23/12/2023 | TARUN KUMAR BHATTACHARYA | 1.81 | 4.77 | 262.69 | 90
25 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Narayanpur (Village code 314899) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000849/2021-2022 | 117/BD-I | 03/02/2022 | 05/03/2022 | ANKUSH CONSTRUCTION & CO. | 13.73 | 11.88 | 86.53 | 100
26 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baliapukur(Village code 314901) under Amaipara (Zone-A) Surface water based Water Supply Scheme of Central Sector Part-I for Murshidabad-Jiaganj Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000753/2021-2022 | 217/BD-I | 24/02/2022 | 10/04/2022 | DAS TRADING CO | 36.42 | 27.95 | 76.75 | 1
27 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Amaipara (Zone-A) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08911 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under AMAIPARA (Zone-A) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I |  | ORD/000120/2023-2024 | 516/BD-I | 25/07/2023 | 23/10/2023 | M/S. M.G. CONSTRUCTION | 102.61 | 0 | 0 | 0
Total | [13 empty] | 721.68 | 371.06 | 51.42