## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Ayesbag Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000758/2021-2022 | 2224/BD-I | 15/12/2021 | 15/03/2022 | TANUSHREE ENTERPRISE | 78.96 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000011/2021-2022 | 146/BD-I | 10/02/2022 | 10/02/2022 | Resource Division | 4.67 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sani Baharapara (Village code 314841) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000222/2021-2022 | 1811/BD-I | 05/10/2021 | 24/11/2021 | M/S. SUKUMAR SINHA | 42.52 | 0 | 0 | 36
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baramganj and Tiktikipara (Village code 314828,314831) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000226/2021-2022 | 1815/BD-I | 05/10/2021 | 24/11/2021 | KAMIRUL SK AND CO. | 50.58 | 0 | 0 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kalikapur Kadamkhandi (Village code 315389) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000227/2021-2022 | 1816/BD-I | 05/10/2021 | 04/12/2021 | M/S GUHA AND ROY ENTERPRISE | 59.54 | 0 | 0 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gopinathpur and Chunakhali (Village code 314829,314830) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000228/2021-2022 | 1817/BD-I | 05/10/2021 | 03/01/2022 | SANJAY BISWAS | 90.82 | 0 | 0 | 85
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khanpur,Hamdampur,Pilkhana and Matijhil (Village code 314845,314846,314850,314848) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JE_RAJIB BISWAS,Junior Engineer-II | ORD/000223/2021-2022 | 1812/BD-I | 05/10/2021 | 13/01/2022 | M/S GUHA AND ROY ENTERPRISE | 95.07 | 0 | 0 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bali (Village code 314832) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-01) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000454/2021-2022 | 1866/BD-I | 07/10/2021 | 05/04/2022 | RAJ KUMAR MONDAL | 100.22 | 0 | 0 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chainpara, Sanyasidanga & Talgachi (Village code 314821, 314822 & 314823) under Ayesbag (Zone-E) Water Supply Scheme of Central Sector Part-I in Murshidabad Jiaganj Block of Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-02) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000557/2021-2022 | 1888/BD-I | 07/10/2021 | 05/04/2022 | M/S SINHA & SONS | 211.59 | 0 | 0 | 65
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Continuation work order for Hiring of one no. Car No. W.B-51B/5774 Bolero Diesel car for official use of Assistant Engineer-I, under Berhampore Division-I, PHE Dte. period for 01.01.2023 to 31.12.2023. | Assistant Engineer-I | JE | ORD/000171/2022-2023 | 1386/BD-I | 23/12/2022 | 23/12/2023 | TARUN KUMAR BHATTACHARYA | 1.81 | 0 | 0 | 100
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gobindapur Lakheraj,Sahamatganj and Bansbari (Village code 314826,314849,314827) under Ayesbag (Zone-E) Surface Water based Water Supply Scheme of Central Sector Part-I in Murshidabad- Jiaganj Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior Engineer-I | ORD/000224/2021-2022 | 1813/BD-I | 05/10/2021 | 28/06/2023 | M/S.TAPAS KUMAR CHAKRABORTY & CO. | 78.62 | 0 | 0 | 100
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Ayesbag (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Part | SM/08912 | Retrofitting | Laying of UPVC distribution pipe Line in connection with JJM (Jal Jeevan Mission) on damaged portion from SBCO brick field to near house Mintu Sen and near house of Ased Sk of Ayesbag water supply scheme under CS Part-I of BD-I, P.H.E Dte. | Assistant Engineer-I |  | ORD/000030/2023-2024 | 129/BD-I | 12/05/2023 | 11/06/2023 | KAUSHIK MAJUMDAR | 2.1 | 0 | 0 | 100
Total | [13 empty] | 948.95 | 0 | 0