## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kulbaria (Village code 315414) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000254/2021-2022 | 1820/BD-I | 05/10/2021 | 03/01/2022 | USHA ENTERPRISE | 84.7 | 0 | 0 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Additional Laying works at village Daulatabad to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission &JalSwapna under Daulatabad Surface water based water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | JE | ORD/000874/2021-2022 | 244/BD-I | 03/03/2022 | 18/03/2022 | MONDAL ENTERPRISE VILL. + P.O.- CHALTIA, P.S.- BERHAMPORE | 8.58 | 0 | 0 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 0 | 0 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Remaining Retrofitting of Functional Household Tap connection (FHTC) in connection with Jal Jeevan Mission under command area of different villages under DAULATABAD(Zone-F) Surface Water based Water Supply Scheme of Central Sector (Part-I) under Murshidabad -Jiaganj Block in Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I |  | ORD/000111/2023-2024 | 440/BD-I | 12/07/2023 | 10/10/2023 | A.P CONSTRUCTION | 42.93 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000006/2021-2022 | 71/BD-I | 28/01/2022 | 28/01/2022 | Resource Division | 0.4 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Material Requisition To Resource Division |  |  | RTOR000002/2021-2022 | 64/BD-I | 27/01/2022 | 27/01/2022 | Resource Division | 1.24 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Purandarpur (Village code 315403) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000234/2021-2022 | 1825/BD-I | 05/10/2021 | 04/12/2021 | M/S SINHA & SONS | 55.92 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dadpur (Village code 315422) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000253/2021-2022 | 1818/BD-I | 05/10/2021 | 13/01/2022 | DOBAY CONSTRUCTION | 98.25 | 0 | 0 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Gauripur and Ruhia (Village code 315412,315413) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000255/2021-2022 | 1821/BD-I | 05/10/2021 | 03/01/2022 | MAMATA USHA ENTERPRISE | 90.65 | 0 | 0 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Daulatabad (Village code 315415) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000232/2021-2022 | 1819/BD-I | 05/10/2021 | 03/01/2022 | PRADIP KUMAR DAS | 88.49 | 0 | 0 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muliarazi,Harirampur and Balia Danga (Village code 315400,315401,315402) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000233/2021-2022 | 1823/BD-I | 05/10/2021 | 24/12/2021 | KAMIRUL SK AND CO. | 76.53 | 0 | 0 | 1
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Doulatabad Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000759/2021-2022 | 2225/BD-I | 15/12/2021 | 15/03/2022 | AJOY GHOSH | 74.29 | 0 | 0 | 1
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chutipur (village code 315419), under Doulatabad (Zone-F) Surface water based Water Supply Scheme of Central Sector Part-I for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000743/2021-2022 | 2205/BD-I | 10/12/2021 | 09/04/2022 | SAMRIDDHI ASSOCIATED | 96 | 0 | 0 | 1
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha,Benidaspur,Garabasa,Maharajpur and Hanumanta Nagar (Village code 315407,315408,315409,315410,315411) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000256/2021-2022 | 1822/BD-I | 05/10/2021 | 13/01/2022 | BANIK BROTHERS | 97.4 | 0 | 0 | 100
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Muli and Gangaprasad (Village code 315406,315423) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000257/2021-2022 | 1824/BD-I | 05/10/2021 | 25/10/2021 | ROY AND ROY CONSTRUCTION | 10.62 | 0 | 0 | 1
16 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Daulatabad (Zone-F) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08913 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mukundapur and Purbagopinathpur (Village code 315416,315420) under Doulatabad (Zone-F) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000258/2021-2022 | 1826/BD-I | 05/10/2021 | 04/11/2021 | SUDIPA SINGHA ROY | 23.87 | 0 | 0 | 1
Total | [13 empty] | 982.31 | 0 | 0