## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hogaldanga (Village code 315432) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000235/2021-2022 | 1829/BD-I | 05/10/2021 | 04/12/2021 | NIRMAL UDYOG | 51.89 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Hajidanga,Baradha,Ganti Baisnab Charan,Kaladanga and Charislampur (Village code 315434,315435 ,315437,315436,315438) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000237/2021-2022 | 1831/BD-I | 05/10/2021 | 24/12/2021 | KAMIRUL SK AND CO. | 73.49 | 65.78 | 89.51 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ruharpara,Baliharpur,Habipur,Dhanaipur,Mirpur and Garamgari (Village code 315426,315427 ,315428,315429,315430,315439) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000238/2021-2022 | 1832/BD-I | 05/10/2021 | 13/01/2022 | M/S GUHA AND ROY ENTERPRISE | 97.55 | 81.51 | 83.56 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nutanpara and Madanpur (Village code 315424,315425) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000239/2021-2022 | 1833/BD-I | 05/10/2021 | 24/12/2021 | M/S GUHA AND ROY ENTERPRISE | 81.18 | 80.7 | 99.42 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Goraipur,Sadipur and Sundalpur (Village code 315417,315418 ,315431) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000236/2021-2022 | 1830/BD-I | 05/10/2021 | 14/11/2021 | M/S SINHA & SONS | 40.25 | 26.91 | 66.85 | 1
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Nidhi Nagar Sarsabad,Char Harharia and Char Panchananpur (Village code 315440,315441,315442) under Habibpur (Zone-G) Surface Water based Water Supply Scheme of Central Sector Part-I in Berhampore Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000581/2021-2022 | 1994/BD-I | 01/11/2021 | 09/02/2022 | NAYLA CONSTRUCTION | 90.2 | 72.42 | 80.29 | 80
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chhayghari (Village code 315433) under Habibpur (Zone-G) Water Supply Scheme of Central Sector Part-I in Berhampore Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-08) | Assistant Engineer-I | JE | ORD/000495/2021-2022 | 1885/BD-I | 07/10/2021 | 05/04/2022 | M/S S.DAS & ENTERPRISE | 275.21 | 151.91 | 55.2 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Habipur (Zone-G) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Par | SM/08914 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Habibpur Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | JE | ORD/000760/2021-2022 | 2226/BD-I | 15/12/2021 | 15/03/2022 | KUNDU CONSTRUCTION | 72.9 | 60.13 | 82.49 | 1
Total | [13 empty] | 915.11 | 547.03 | 59.78