## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Chaltia (Village code 315450) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE.Dte. (Sl-01) | Assistant Engineer-I | Junior Engineer-I | ORD/000569/2021-2022 | 1955/BD-I | 27/10/2021 | 25/04/2022 | UNICON INDIA | 267.92 | 90.56 | 33.8 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Additional laying work of 300 mm dia DI Pipe Line at pond side of near Chumrigacha Primary School due to damage of UPVC Pipe line and with allied works of Distribution pipe line under Bairgachi Surface Water based Water Supply Scheme under Berhampore Division - I, PHE Dte.in Murshidabad District | Assistant Engineer-I | Junior Engineer-I | ORD/000004/2022-2023 | 547/BD-I | 13/05/2022 | 23/05/2022 | JIBENDRA NARAYAN SUKUL | 4.54 | 4.31 | 94.79 | 45
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Math Binkar (Village code 315366) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-II |  | ORD/000468/2021-2022 | 1870/BD-I | 07/10/2021 | 06/12/2021 | M/S ADHIKARI CONSTRUCTION | 6.47 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Fate Sing Diar and Char Narayanpur (Village code 315364,315384) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior Engineer-I | ORD/000246/2021-2022 | 1841/BD-I | 05/10/2021 | 04/12/2021 | UNIVERSE UNEMPLOYED ENGINEERS CO. OPT. & CONSTRUCTION SOCIETY LTD. | 55.84 | 18.71 | 33.51 | 40
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baikunthapur (Village code 315369) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I | Junior Engineer-I | ORD/000469/2021-2022 | 1871/BD-I | 07/10/2021 | 05/01/2022 | M/S BIMALENDU BOSE | 22.56 | 21.5 | 95.32 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bairgachi Village- village code-315382, Habitation-Char Begpur (ID-0001295651) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID - 0001756485 | Assistant Engineer-I |  | ORD/000470/2021-2022 | 1872/BD-I | 07/10/2021 | 06/12/2021 | TANUSHREE ENTERPRISE | 14.92 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Mankara, Bezpara, Baragachi, Paschim Narayanpur (Village code 315365, 315368, 315382 & 315383) respectively under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-15) | Assistant Engineer-I | Junior Engineer-I | ORD/000558/2021-2022 | 1889/BD-I | 07/10/2021 | 05/04/2022 | M/S S.S ENTERPRISE ALAMPUR, NODAKHALI, SOUTH 24 PARGANAS | 296.55 | 139.52 | 47.05 | 1
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhyanagar village-Village Code-315449, Habitation-Belia khari (ID-0001295654) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. Scheme ID ? 0001756485 | Assistant Engineer-I |  | ORD/000471/2021-2022 | 1873/BD-I | 07/10/2021 | 05/01/2022 | J.S. CONSTRUCTION | 22.08 | 21.87 | 99.06 | 0
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2023 to 31.01.2024. | Assistant Engineer-I | JE | ORD/000128/2023-2024 | 517/BD-I | 25/07/2023 | 25/01/2024 | SOUVIK HALDER | 0.91 | 2.39 | 263.26 | 10
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2024 to 31.07.2024. | Assistant Engineer-I | JE | ORD/000427/2023-2024 | 131/BD-I | 31/01/2024 | 31/07/2024 | SOUVIK HALDER | 0.91 | 2.39 | 263.53 | 100
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2024 to 31.01.2025. | Assistant Engineer-I | JE | ORD/000262/2024-2025 | 1195/BD-I | 26/07/2024 | 26/01/2025 | SOUVIK HALDER | 0.91 | 2.38 | 262.55 | 0
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.02.2025 to 31.07.2025. | Assistant Engineer-I | JE | ORD/000384/2024-2025 | 193/BD-I | 30/01/2025 | 30/07/2025 | SOUVIK HALDER | 0.91 | 1.6 | 176.02 | 0
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Continuation Work order for Hiring of one no. Car No- WB 57E-7081 Innova Diesel car for official use of Executive Engineer, Berhampore Division-I, PHE Dte. period for 01.08.2025 to 31.10.2025. | Assistant Engineer-I | JE | ORD/000094/2025-2026 | 991/BD-I | 31/07/2025 | 31/10/2025 | SOUVIK HALDER | 0.45 | 0 | 0 | 0
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Baninathpur (Village code 315367) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000247/2021-2022 | 1842/BD-I | 05/10/2021 | 24/11/2021 | JIBENDRA NARAYAN SUKUL | 41.36 | 41.73 | 100.91 | 1
16 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Bhatpara (Village code 315370) under Bairgachi (Zone- C) Surface water based Water Supply Scheme of Central Sector Part-II for Berhampore Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000248/2021-2022 | 1843/BD-I | 05/10/2021 | 04/11/2021 | PROSENJIT DAS | 24.41 | 21.86 | 89.55 | 1
17 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Formal Work order for Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under Command area of village of Haridasmati (Village code 315451) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-06) | Assistant Engineer-I | Junior Engineer-I | ORD/000450/2021-2022 | 1882/BD-I | 07/10/2021 | 05/04/2022 | DHIMAN SARKAR | 88.21 | 78.75 | 89.28 | 50
18 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Laying of different dia UPVC distribution pipeline with allied works along with attached sheet of node point over command area of Chaltia village of Bhakuri-I gram panchayat under Bairgachi Water Supply Scheme,Central Sector Part-II under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I |  | ORD/000379/2021-2022 | 1463/BD-I | 16/08/2021 | 15/10/2021 | MITRA & SARKAR CONSTRUCTION | 51.34 | 10.12 | 19.72 | 0
19 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Laying of Pipeline network within unlaid portion and damaged portion of pipeline within command area of Bairgachi Surface Water based Water Supply Scheme in connection with providing FHTC work under Berhampore Division - I, PHE Dte. (Phase-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000761/2021-2022 | 2227/BD-I | 15/12/2021 | 15/03/2022 | JIBENDRA NARAYAN SUKUL | 74.65 | 77.64 | 104 | 1
20 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Additional Laying works at village Bhatpara ( Village code-315370) to facilitate Functional Household Tap Connection (FHTC) works in connection to JalJeevan Mission & JalSwapna under Bairgachi (Zone-C) Surface water supply scheme of Central Sector Part-II (Berhampore,Block) under Berhampore Division-I, PHE Dte. In the District of Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000842/2021-2022 | 98/BD-I | 01/02/2022 | 16/02/2022 | MINA DAS | 8.88 | 7.63 | 85.95 | 1
21 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Laying of 350 mm dia DI (K-7) distribution Pipeline including allied works along with attached sheet of node point over command area of Bhakuri-I G.P under Bairgachi W/S scheme under Berhampore Division -I ,P.H.E Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000009/2022-2023 | 552/BD-I | 13/05/2022 | 27/06/2022 | DHIMAN SARKAR | 20.59 | 6.02 | 29.25 | 100
22 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Additional Laying works at village Ajodhya Nagar & Chumrigacha to faciliate Functional Household Tap connection(FHTC) works in connection to Jal Jeevan Mission under Bairgachi (Zone-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000001/2023-2024 | 21/BD-I | 11/04/2023 | 11/05/2023 | JIBENDRA NARAYAN SUKUL | 50.51 | 50.5 | 99.98 | 100
23 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Laying of different dia DI pipe Line in connection with JJM (Jal Jeevan Mission) over damaged portion with allied works at Karim more and near Balarampur High School for smooth running of FHTC Work under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte | Assistant Engineer-I | Junior Engineer-I | ORD/000014/2023-2024 | 85/BD-I | 03/05/2023 | 02/06/2023 | JIBENDRA NARAYAN SUKUL | 5.69 | 4.97 | 87.33 | 100
24 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ajodhya Nagar (Village code 315449) under Bairgachi (Zone-C) Water Supply Scheme of Central Sector Part-II in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-05) | Assistant Engineer-I | Junior Engineer-I | ORD/000452/2021-2022 | 1883/BD-I | 07/10/2021 | 05/04/2022 | TARUN KUMAR BHATTACHARYA | 133.38 | 121.89 | 91.38 | 50
25 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Laying of UPVC pipe Line in connection with JJM (Jal Jeevan Mission) with allied works near Balarampur Halt Station under Bairgachi (Zone-C) surface based water supply scheme under CS Part-II of BD-I, P.H.E Dte. | Assistant Engineer-II |  | ORD/000017/2023-2024 | 88/BD-I | 03/05/2023 | 02/06/2023 | KAUSHIK MAJUMDAR | 3.5 | 3.48 | 99.41 | 100
26 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Balance Laying and allied works at village Ajodha nagar & Chumrigacha to facilitate Functional Household Tap connection (FHTC) Works in connection to Jal Jeevan Mission under Bairgachi(ZONE-C) surface water based Water Supply Scheme of Central Sector Part-II under Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000375/2023-2024 | 119/BD-I | 30/01/2024 | 30/03/2024 | JIBENDRA NARAYAN SUKUL | 10.28 | 10.26 | 99.75 | 100
27 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Balance and Additional Work of Laying and Improvement of Office cum Godown building at OHR site of Bairgachhi Water Supply Scheme of Central Sector Part-II, under JJM within Berhampore block in the district of Murshidabad under Berhampore Division-I, P.H.Engineering Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000121/2024-2025 | 1464/BD-I | 06/09/2024 | 02/12/2024 | JIBENDRA NARAYAN SUKUL | 26.42 | 6.98 | 26.44 | 100
28 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Improvement of Rising main and distribution system for providing drinking water facility to the local habitation within command area of Purbanarayanpur Zone of Central Sector Part-II under JJM within Berhampore block of Murshidabad district under Berhampore Division-I, P.H.E. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000125/2024-2025 | 1473/BD-I | 06/09/2024 | 05/11/2024 | JAMIRUL CONSTRUCTION | 11.25 | 2.88 | 25.61 | 100
29 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Bairgachi (Zone-C) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (Pa | SM/08916 | Retrofitting | Addittional work for retrofitting and Laying of distribution pipeline of BAIRAGACHI and allied works under JJM within Berhampore Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-I,Assistant Engineer-II | JE | ORD/000143/2024-2025 | 1612/BD-I | 03/10/2024 | 18/10/2024 | JIBENDRA NARAYAN SUKUL | 2.48 | 0 | 0 | 100
Total | [13 empty] | 1380.34 | 757.6 | 54.89