## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Supply of Gun Metal Ferrule Conforming to IS 2692/1994 (reaffirmed 2005) ISI Marked for the work of Central Sector (Part-II) Water Supply Scheme for FHTC (Functional Household Tap Connection) under Berhampore Division - I, PHE Dte. Dist Murshidabad | Assistant Engineer-I,Assistant Engineer-II | JE,JE_RAJIB BISWAS,Junior Engineer-I,Junior Engineer-II | ORD/000463/2020-2021 | 88/ BD-I | 20/01/2021 | 19/07/2021 | FNC CONSTRUCTION AND CO. | 132.44 | 7.66 | 5.79 | 1
2 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jhanjha (village code 315503) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000741/2021-2022 | 242/BD-I | 03/03/2022 | 23/03/2022 | ANKITA ENTERPRISE | 4.64 | 3.4 | 73.24 | 1
3 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur Ramna (village code 315497) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000731/2021-2022 | 153/BD-I | 11/02/2022 | 22/04/2022 | GOSWAMI TRANSPORT & ENGINEERING WORKS | 59.15 | 41.11 | 69.5 | 1
4 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Ramkrishnapur (village code 315490) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. |  |  | ORD/000736/2021-2022 | 2251/BD-I | 21/12/2021 | 04/02/2022 | S DUTTA | 28.82 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Formal Work Order for Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Swaruppur (Village code 315505) under Lochanmati (Zone-E) Water Supply Scheme of Central Sector Part-II in Hariharpara Block in Murshidabad District under Berhampore Division - I, PHE Dte. (Sl-10) | Assistant Engineer-II |  | ORD/000498/2021-2022 | 1905/BD-I | 08/10/2021 | 06/04/2022 | M/S RUBIET HOSSAIN | 144.19 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Lochanmati Dangapara (village code 315498) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000729/2021-2022 | 2201/BD-I | 10/12/2021 | 10/03/2022 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 85.79 | 81.81 | 95.36 | 1
7 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Kaludiar (village code 315501) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000733/2021-2022 | 154/BD-I | 11/02/2022 | 28/03/2022 | MUNNA AGROTECH ENTERPRISE | 34.19 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Tekona (village code 315492) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE,Junior Engineer-II | ORD/000734/2021-2022 | 186/BD-I | 18/02/2022 | 20/08/2025 | DAS ENTERPRISE | 32.28 | 0 | 0 | 70
9 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sankarpur (village code 315489) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000730/2021-2022 | 2202/BD-I | 10/12/2021 | 30/10/2023 | UTTAM MUKHERJEE | 76.01 | 65.33 | 85.96 | 87
10 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Dharampur (village code 315496) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000739/2021-2022 | 2304/BD-I | 28/12/2021 | 27/01/2022 | SUKUMAR ROY | 22.73 | 21.68 | 95.37 | 1
11 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Janarddanpur (village code 315493) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000740/2021-2022 | 155/BD-I | 11/02/2022 | 13/03/2022 | ANKITA ENTERPRISE-GOPEJAN(NATHPARA) | 10.56 | 10.17 | 96.3 | 1
12 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Siddhi Nandi (village code 315504) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | JE | ORD/000732/2021-2022 | 241/BD-I | 03/03/2022 | 17/04/2022 | PRANAB KUMAR GHOSH | 36.64 | 30.74 | 83.89 | 85
13 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Jamlabad (village code 315495) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000742/2021-2022 | 156/BD-I | 11/02/2022 | 03/03/2022 | U.S BUILDERS | 7.58 | 5.6 | 73.87 | 1
14 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Sundalpur (village code 315502) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000737/2021-2022 | 2204/BD-I | 10/12/2021 | 09/01/2022 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 24.6 | 22.86 | 92.93 | 1
15 | MURSHIDABAD |  | Berhampore Division I | Retrofitting For Providing Functional Household Tap Connection (FHTC) In Connection With Jal Jeevan Mission And Jal Swapna Under Command Area Of Lochanmati (Zone-E) Surface Water Based Water Supply Scheme In The Arsenic Affected Areas Of Central Sector (P | SM/08917 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Khamarbati (village code 315494) under Lochanmati (Zone-E) Surface water based Water Supply Scheme of Central Sector Part-II for Hariharpara Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-II | Junior Engineer-II | ORD/000738/2021-2022 | 2253/BD-I | 21/12/2021 | 20/01/2022 | RAJEN DAS | 24.27 | 22.02 | 90.74 | 1
Total | [13 empty] | 723.89 | 312.38 | 43.15