## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Bramhottor (Habitation ID-0001294213 ) and Ilishmari (Habitation ID-0001792563) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000226/2020-2021 | 990/BD-I | 17/12/2020 | 15/02/2021 | S. K. ENTERPRISE | 11.8 | 8.87 | 75.2 | 1
2 | MURSHIDABAD |  | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area at Kaharpara (Habitation ID-0001294214 ) and Santalpara (Habitation ID-0001792540) in the village of Bramhottor Manikchak (Village code 314234) under Bramhottor Manikchak Ground Water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I |  | ORD/000222/2020-2021 | 986/BD-I | 17/12/2020 | 17/03/2021 | MS RUBIET HOSSAIN | 42.55 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of B.M. Para,Bausmari and Bramhottor Manikchak (Habitation ID 0001792822,0001792589,0001294212) under Bramhottor Manikchak Ground Water based Water Supply Scheme in Lalgola Block,of Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000245/2021-2022 | 1855/BD-I | 07/10/2021 | 26/11/2021 | KAMIRUL SK AND CO. | 48.43 | 0 | 0 | 1
4 | MURSHIDABAD |  | Berhampore Division I | RETROFITTING FOR PROVIDING FUNCTIONAL HOUSEHOLD TAP CONNECTION (FHTC) IN CONNECTION WITH JAL JEEVAN MISSION AND JAL SWAPNA IN THE COMMAND AREA OF BRAHIMOTTAR MANIKCKCHAK GROUND WATER SUPPLY SCHEME UNDER LALGOLA BLOCK IN MURSHIDABAD DISTRICT UNDER BERHAM | SM/08919 | Retrofitting | Providing Retrofitting Functional Household Tap Connection (FHTC) in connection with Jal Jeevan Mission and Jal Swapna under command area of village of Paschim Diarmanik chak (village code 314228) under BRAHIMOTTAR MANIKCHAK Ground water based Water Supply Scheme for Lalgola Block, in Murshidabad District under Berhampore Division - I, PHE Dte. | Assistant Engineer-I | JE | ORD/000748/2021-2022 | 2250/BD-I | 21/12/2021 | 04/02/2022 | ARINDAM MAJUMDAR | 30.87 | 0 | 0 | 1
Total | [13 empty] | 133.65 | 8.87 | 6.64