## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Extension of pipe line from existing PWSS to different Anganwadi Centers (AWCs), located within the command area of PWSS. | SM/09026 | Anganwadi | Water Supply arrangement by 75 mm dia UPVC Pipeline from adjacent Existing PWSS having Electrical Power Connections different Anganwadi Centres under different Dev. Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I,Assistant Engineer-II | JE,Junior Engineer-I | ORD/000288/2021-2022 | 1376/BD-I | 30/07/2021 | 25/05/2025 | MAMATA USHA ENTERPRISE | 485.97 | 0 | 0 | 75
Total | [13 empty] | 485.97 | 0 | 0