## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD | Nawda | Berhampore Division I | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | New | Material Requisition To Resource Division |  |  | RTOR000104/2023-2024 | 201/BD-1/3 | 10/02/2024 | 10/02/2024 | Resource Division | 2.51 | 0 | 0 | 0
2 | MURSHIDABAD | Nawda | Berhampore Division I | MOKTARPUR PIPED WATER SUPPLY SCHEME | SM/11620 | New | Commissioning of Moktarpur ground water based Pipe water Supply scheme under Jal Swapna at NAWDA Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE | ORD/000044/2023-2024 | 117/BD-I | 10/05/2023 | 31/12/2025 | M/S GOUTAM CHAKRABORTY | 233.73 | 105.09 | 44.96 | 75
Total | [13 empty] | 236.24 | 105.09 | 44.48