## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of BUNDHAR KISMAT ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000816/2023-2024 | 3766/MEDB | 03/11/2023 | 03/02/2024 | GANGULI ELECTRICAL CO. | 11.19 | 9.3 | 83.1 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000059/2023-2024 | 196/BD-I/6 | 09/02/2024 | 09/02/2024 | Resource Division | 48.07 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | BHUNDAR KISMAT PWSS |  |  | BILL/01451/2023-2024 | 350/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 7.83 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | Augmentation of Bhundar kismat Piped water supply scheme to accommodate construction of pump house ,boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000201/2022-2023 | 1617/BD-I | 02/03/2023 | 29/08/2023 | DHIRENDRA NATH MONDAL | 222.61 | 186.56 | 83.8 | 60
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BHUNDAR KISMAT Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000885/2021-2022 | 268/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 100 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bhundar Kismat | SM/12578 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Bhundar Kismat ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000106/2022-2023 | 1362/BD-I | 21/12/2022 | 11/09/2024 | GHOSH BUILDERS | 2.41 | 0 | 0 | 100
Total | [13 empty] | 294.81 | 198.55 | 67.35