## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DAKSHIN HANUMANTNAGAR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000818/2023-2024 | 3767/MEDB | 03/11/2023 | 03/02/2024 | ASSOCIATED ELECTRICAL CO. | 11.19 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000063/2023-2024 | 196/BD-I/10 | 09/02/2024 | 09/02/2024 | Resource Division | 102.96 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Augmentation of DAKSHIN HANUMANTANAGAR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000193/2023-2024 | 744/BD-I | 17/08/2023 | 11/07/2026 | M/S SINHA & SONS | 478.03 | 0 | 0 | 45
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DAKSHIN HANUMANTANAGAR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000877/2021-2022 | 261/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.77 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd/3rd site) and Allied Works for Dakshin Hanumantanagar ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE | ORD/000102/2022-2023 | 1359/BD-I | 21/12/2022 | 20/01/2023 | PRANAB KUMAR GHOSH | 3.8 | 0 | 0 | 72
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Dakshin Hanumantanagar | SM/12579 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) forDakshinHanumantanagar water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000259/2023-2024 | 1028/BD-I | 01/11/2023 | 01/12/2023 | SANTANU BISWAS | 9.48 | 0 | 0 | 100
Total | [13 empty] | 608.24 | 0 | 0