## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000061/2023-2024 | 196/BD-I/8 | 09/02/2024 | 09/02/2024 | Resource Division | 10.99 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | Augmentation | Augmentation of Diar Syampur Zone-II Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000200/2022-2023 | 1623/BD-I | 02/03/2023 | 31/12/2024 | SANDHAN ADHIKARY | 152.01 | 56.56 | 37.21 | 40
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | Augmentation | Balance work for the work of Laying distribution pipe line of Diar Syampur Zone-II PWSS under Jal Jeevan Mission within Bhagwangola-I block in connection with Augmentation under Berhampore Division-I,PHE.Dte. In the district of Murshidabad. | Assistant Engineer-I |  | ORD/000055/2025-2026 | 767/BD-I | 22/05/2025 | 20/08/2025 | SANDHAN ADHIKARI | 69.54 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- II | SM/12580 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-II Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000880/2021-2022 | 264/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.44 | 2.39 | 97.91 | 100
Total | [13 empty] | 234.97 | 58.95 | 25.09