## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of DIGHA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000030/2023-2024 | 3729/MEDB | 03/11/2023 | 03/02/2024 | SURAKSHA | 11.18 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000062/2023-2024 | 196/BD-I/9 | 09/02/2024 | 09/02/2024 | Resource Division | 3.75 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Formal work order for Augmentation of DIGHA Piped water supply scheme to accommodate contruction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer | ORD/000135/2022-2023 | 1822/BD-I | 31/03/2023 | 01/01/2025 | SUJIT KUMAR SAHA | 255.85 | 27.9 | 10.91 | 10
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of DIGHA PWSS under Jal Jeevan Mission within Bhagwangola-I inconnection with Augmentation under Berhampore Division-I , P.H.E. Dte. In the districtof Murshidabad. | Assistant Engineer-I |  | ORD/000048/2025-2026 | 755/BD-I | 22/05/2025 | 21/06/2025 | DEBASISH SARKAR | 24.4 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIGHA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000878/2021-2022 | 262/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.43 | 2.43 | 100 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Digha ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE | ORD/000107/2022-2023 | 1364/BD-I | 21/12/2022 | 20/01/2023 | SELIM SARKAR | 2.27 | 1.73 | 76.05 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Digha Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS,Junior Engineer | ORD/000394/2023-2024 | 160/BD-I | 05/02/2024 | 06/03/2024 | M/S D. PALIT & CO. | 9 | 7.74 | 85.96 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Digha | SM/12581 | Augmentation | Improvement of R.C.C Elevaced Reservoir (225 Cum) of Ground Water Based Supply Scheme for Augmentation of Digha Water Supply Scheme under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I | Junior Engineer | ORD/000007/2024-2025 | 895/BD-I | 06/06/2024 | 06/07/2024 | K.B CONSTRUCTION | 6.7 | 0 | 0 | 100
Total | [13 empty] | 315.58 | 39.8 | 12.61