## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Executive Engineer under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000693/2022-2023 | 658/AE/MEDB | 31/03/2023 | 30/09/2023 | M/S SAJAHAN CHOWDHURY | 0.9 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of PASCHIM RAMPUR ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000834/2023-2024 | 3775/MEDB | 03/11/2023 | 03/02/2024 | MERCURY ENGINEERING CO | 22.4 | 0 | 0 | 8
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Continuation Order Hiring of Diesel driven Bolero/Equivalent four wheeler car for the official use of the Assistant Engineer-I under Office of the Executive Engineer, Mechanical/electrical Division, PHE Dte. in the district of Murshidabad. | ASSISTANT ENGINEER-I | Junior engineer-III | ORD/000758/2022-2023 | 237/MEDB | 27/01/2023 | 27/03/2023 | M/S SAJAHAN CHOWDHURY | 0.29 | 0 | 0 | 10
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000087/2023-2024 | 196/BD-I/15 | 09/02/2024 | 09/02/2024 | Resource Division | 41.52 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Paschim Rampur ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. " | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000010/2025-2026 | 1134/MEDB | 13/05/2025 | 13/08/2025 | M/S SAJAHAN CHOWDHURY | 49.94 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Formal Work order for Augmentation of PASCHIM RAMPUR Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000160/2022-2023 | 1453/BD-I | 17/01/2023 | 01/01/2026 | NILKAMAL BASAK | 398.64 | 0 | 0 | 20
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at PASCHIMRAMPUR PWSS (TW-III Site) within BHAGWANGOLA-I Block under JAL JEEVAN MISSION in connection with Augmentation work under Berhampore Division-I, P.H.Engineering Dte. (01 No TW) | Assistant Engineer-I |  | ORD/000063/2025-2026 | 776/BD-I | 22/05/2025 | 06/06/2025 | M/S GHOSH ENTERPRISE | 9 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Paschim Rampur ground water supply scheme in Bhagwangola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-90.00 Cum/Hr.) | Assistant Engineer-I |  | ORD/000017/2025-2026 | 614/BD-I | 22/04/2025 | 16/02/2026 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 207.69 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for PASCHIM RAMPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000876/2021-2022 | 260/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.82 | 0 | 0 | 100
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Paschim Rampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000012/2023-2024 | 59/BD-I | 25/04/2023 | 25/05/2023 | SAIF TRADERS | 2.05 | 0 | 0 | 100
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Paschim Rampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | Junior Engineer-I | ORD/000032/2023-2024 | 124/BD-I | 12/05/2023 | 30/06/2025 | HARUN ALL RASHID & BROTHERS | 17.74 | 0 | 0 | 50
12 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Paschim Rampur | SM/12583 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (350 Cum) for Paschim Rampur water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | Junior Engineer-I | ORD/000279/2023-2024 | 996/BD-I | 30/10/2023 | 08/08/2024 | B.M. ENTERPRISE | 8.53 | 0 | 0 | 100
Total | [13 empty] | 761.52 | 0 | 0