## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Hasanpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000034/2023-2024 | 3731/MEDB | 03/11/2023 | 03/02/2024 | GANGULI ELECTRICAL CO. | 11.46 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000050/2023-2024 | 196/BD-I/1 | 09/02/2024 | 09/02/2024 | Resource Division | 2.08 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Augmentation of Hasanpur Piped water supply scheme to accommodate construction of OHR,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Swapna in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000119/2023-2024 | 831/BD-I | 01/09/2023 | 07/07/2024 | A ONE CONSTRUCTION | 238.41 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HASANPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000889/2021-2022 | 272/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.53 | 2.53 | 100 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hasanpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000116/2022-2023 | 1366/BD-I | 21/12/2022 | 20/01/2023 | SARIFUL ISLAM | 2.49 | 2.45 | 98.4 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Replacement of sand layers, Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 30.50 Cum/hr) at Hasanpur Water Supply Scheme under Jal Jivan Mission of Bhagwangola-II Block under Berhampore Div-I, Murshidabad PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000017/2024-2025 | 925/BD-I | 07/06/2024 | 07/07/2024 | M/S GOUTAM CHAKRABORTY | 22.46 | 22.43 | 99.89 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Improvement of R.C.C Elevaced Reservoir (136 Cum) of Ground Water Based Supply Scheme for Augmentation of Hasanpur Water Supply Scheme of Bhagwangola-II block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000022/2024-2025 | 935/BD-I | 10/06/2024 | 05/02/2025 | REBEKA MONDAL | 4.85 | 4.71 | 97.21 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hasanpur | SM/12584 | Augmentation | Balance works for Improvement of existing AIRP ( Modified Sujapur Sadipur Model, Capacity 30.50 Cum/hr) and alled works at Hasanpur Water Supply Scheme under Jal Jeevan Mission within Bhagwangola-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad.. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000052/2025-2026 | 761/BD-I | 22/05/2025 | 21/06/2025 | M/S GOUTAM CHAKRABORTY | 2.99 | 0 | 0 | 100
Total | [13 empty] | 287.28 | 32.13 | 11.18