## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | Augmentation | Name of Work: Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Harirampur ground water based water supply scheme under Block- BHAGAWANGOLA-II Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001482/2023-2024 | 761/MEDB | 20/02/2024 | 20/05/2024 | ASSOCIATED ELECTRICAL CO. | 10.35 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000048/2023-2024 | 196/BD-I/4 | 09/02/2024 | 09/02/2024 | Resource Division | 116.19 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | Augmentation | Formal work order for Augmentation of HARIRAMPUR Piped water supply scheme to accommodate construction of OHR, Service Road, Laying of Design Pipe Line and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I, PHE. Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000136/2022-2023 | 1445/BD-I | 17/01/2023 | 15/07/2026 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 310.02 | 93.79 | 30.25 | 65
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HARIRAMPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000890/2021-2022 | 273/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.45 | 2.45 | 100 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Harirampur to Accommodate FHTC. | SM/12586 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Harirampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000169/2022-2023 | 1440/BD-I | 16/01/2023 | 15/02/2023 | K.B CONSTRUCTION | 2.41 | 2.39 | 99.46 | 100
Total | [13 empty] | 441.42 | 98.63 | 22.34