## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000065/2023-2024 | 196/BD-I/12 | 09/02/2024 | 09/02/2024 | Resource Division | 3.11 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Gobra Water Supply Scheme |  |  | BILL/01456/2023-2024 | 349/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 3.07 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Gobra ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000011/2025-2026 | 1136/MEDB | 13/05/2025 | 13/08/2025 | DEY ENTERPRISE (MALDA) | 39.59 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of GOBRA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000032/2023-2024 | 3730/MEDB | 03/11/2023 | 01/09/2025 | SARKAR CONSTRUCTION | 11.46 | 9.53 | 83.14 | 15
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Augmentation of GOBRA Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road,laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE,Junior Engineer | ORD/000194/2023-2024 | 745/BD-I | 17/08/2023 | 01/08/2025 | DAS TRADING CO | 315.08 | 16.72 | 5.31 | 21
6 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC, Block Bhagwangola-I of Murshidabad District under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000543/2024-2025 | 329/MEDB | 10/02/2025 | 10/05/2025 | MASSK ENGINEERING WORKS | 11.36 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after successful completion of 3 (Three) months Trial Run of "Augmentation of Gobra ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I | Junior Engineer | ORD/000333/2024-2025 | 286/BD-I | 12/02/2025 | 09/12/2025 | MODERN CONSTRUCTION | 122.8 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Improvement of Existing AIRP (Modified Sujapur Sadipur Model, Capacity 30.00 cum/hr) including required allied works of GOBRA PWSS under Jal Jeevan Mission within Bhagwangola-I interconnection with Augmentation under Berhampore Division-I, P.H.E. Dte. In the districtof Murshidabad.. | Assistant Engineer-I |  | ORD/000053/2025-2026 | 762/BD-I | 22/05/2025 | 21/06/2025 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 9.68 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for GOBRA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000882/2021-2022 | 266/ BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.71 | 2.61 | 96.43 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) for Gobra water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | Junior Engineer | ORD/000251/2023-2024 | 1010/BD-I | 31/10/2023 | 30/11/2023 | ANKITA ENTERPRISE-GOPEJAN (NATHPARA) | 6.7 | 6.42 | 95.83 | 100
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Gobra to Accommodate FHTC. | SM/12587 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Gobra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | Junior Engineer | ORD/000393/2023-2024 | 159/BD-I | 05/02/2024 | 06/03/2024 | M/S D. PALIT & CO. | 9 | 0 | 0 | 100
Total | [13 empty] | 534.56 | 35.27 | 6.6