## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of TELIA ground water based water supply scheme under Block- Bhagawangola-I, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000043/2023-2024 | 3736/MEDB | 03/11/2023 | 03/02/2024 | M/S K.P. PRAMANIK | 11.45 | 0 | 0 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000066/2023-2024 | 196/BD-I/13 | 09/02/2024 | 09/02/2024 | Resource Division | 8.05 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Telia Water Supply Scheme |  |  | BILL/01455/2023-2024 | 348/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 4.3 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Telia ground water supply scheme in Bhagwabgola-I Block Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000012/2025-2026 | 1137/MEDB | 13/05/2025 | 13/08/2025 | DEY ENTERPRISE | 39.98 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Formal work order for Augmentation of Telia Piped water supply scheme to accommodate construction of OHR, toilet ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000134/2022-2023 | 1446/BD-I | 17/01/2023 | 16/07/2025 | MUNNA AGROTECH ENTERPRISE | 338.52 | 0 | 0 | 80
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Allied work for construction of Cast-in-situ Pile (grade M30) (Shaft Length 25 Mtr.) to accommodate construction of OHR, pump house, boundary wall and road restoration of Augmentation of TELIA Piped water supply scheme under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000157/2024-2025 | 1629/BD-I | 04/10/2024 | 30/03/2025 | MUNNA AGROTECH ENTERPRISE | 50.58 | 0 | 0 | 90
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for TELIA Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000883/2021-2022 | 267/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.63 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Telia to Accommodate FHTC. | SM/12588 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Telia ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | Junior Engineer-I | ORD/000105/2022-2023 | 1360/BD-I | 21/12/2022 | 12/10/2024 | PRAVAT KUMAR GHOSH | 2.41 | 0 | 0 | 100
Total | [13 empty] | 457.91 | 0 | 0