## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000257/2022-2023 | 1679/BD-I | 14/03/2023 | 13/04/2023 | TAHID SK | 2.41 | 0 | 0 | 100
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of HAZI MAHAMMADPUR, Zone-I ground water based water supply scheme under Block- Lalgola, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000091/2023-2024 | 3782/MEDB | 03/11/2023 | 03/02/2025 | ARINDAM MAJUMDAR | 10.45 | 0 | 0 | 10
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000073/2023-2024 | 201/BD-1/14 | 10/02/2024 | 10/02/2024 | Resource Division | 21.36 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000013/2024-2025 | 1510/BD-I/7 | 12/09/2024 | 12/09/2024 | Resource Division | 2.3 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000015/2025-2026 | 1150/MEDB | 14/05/2025 | 14/08/2025 | JAL PRAVAHIKA PVT LTD | 39.61 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Augmentation of Hazi Mohammadpur Zone-I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000213/2022-2023 | 1550/BD-I | 17/02/2023 | 16/08/2023 | N.H ENTERPRISE | 61.96 | 0 | 0 | 95
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Hazi Mahammadpur Zone-I ground water supply scheme in Lalgola Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer |  | ORD/000088/2025-2026 | 948/BD-I | 18/07/2025 | 14/05/2026 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Improvement of existing AIRP(Gober Danga Model) ( Capacity - 21.0 Cum/ Hr.) of Hazi Mahammadpur Zone-II Water supply Scheme under Jal Jeevan Mission within Lalgola block under Berhampore Division - I, P.H.E Dte. In the district of Murshidabad. | Assistant Engineer |  | ORD/000078/2025-2026 | 845/BD-I | 23/06/2025 | 07/08/2025 | ABIDA CONSTRUCTION | 22.63 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000893/2021-2022 | 278/BD-I | 08/03/2022 | 18/03/2022 | ENVIROTECH SOLUTIONS | 2.46 | 0 | 0 | 1
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hazi Mohammadpur Zone - I Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000031/2023-2024 | 123/BD-I | 12/05/2023 | 11/06/2023 | HARUN ALL RASHID & BROTHERS | 8.83 | 0 | 0 | 100
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - I to Accommodate FHTC. | SM/12589 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-I of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer | JE | ORD/000358/2023-2024 | 16/BD-I | 04/01/2024 | 31/08/2024 | AHONA ENTERPRISE | 6.67 | 0 | 0 | 100
Total | [13 empty] | 301.48 | 0 | 0