## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-II ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000119/2022-2023 | 1443/BD-I | 16/01/2023 | 26/01/2023 | MIR SABNAM BEGUM | 2.37 | 2.33 | 98.4 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 201/BD-1/15 | 10/02/2024 | 10/02/2024 | Resource Division | 15.25 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 1510/BD-I/12 | 12/09/2024 | 12/09/2024 | Resource Division | 1.31 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Augmentation of Hazi Mohammadpur Z-II Piped water supply scheme to accommodate construction of service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000191/2022-2023 | 1457/BD-I | 17/01/2023 | 16/07/2023 | MODERN CONSTRUCTION | 45.93 | 39.48 | 85.97 | 60
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-II of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000280/2023-2024 | 997/BD-I | 30/10/2023 | 21/06/2025 | TANBEER CONSTRUCTION | 6.76 | 5 | 73.86 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000894/2021-2022 | 279/BD-I | 08/03/2022 | 18/03/2022 | ENVIROTECH SOLUTIONS | 2.46 | 2.45 | 99.31 | 1
7 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of HAZI MAHAMMADPUR, Zone-II ground water based water supply scheme under Block- Lalgola, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000093/2023-2024 | 3783/MEDB | 03/11/2023 | 01/09/2025 | DAS ENTERPRISE (CHOA) | 10.29 | 8.36 | 81.24 | 15
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hazi Mohammadpur Zone - II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000028/2023-2024 | 83/BD-I | 03/05/2023 | 02/06/2023 | HARUN ALL RASHID & BROTHERS | 8.83 | 7.49 | 84.84 | 100
Total | [13 empty] | 93.2 | 65.11 | 69.86