## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Hazi Mohammadpur Zone-II ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000119/2022-2023 | 1443/BD-I | 16/01/2023 | 26/01/2023 | MIR SABNAM BEGUM | 2.37 | 2.33 | 98.4 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000074/2023-2024 | 201/BD-1/15 | 10/02/2024 | 10/02/2024 | Resource Division | 15.25 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000018/2024-2025 | 1510/BD-I/12 | 12/09/2024 | 12/09/2024 | Resource Division | 1.31 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Augmentation of Hazi Mohammadpur Z-II Piped water supply scheme to accommodate construction of service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000191/2022-2023 | 1457/BD-I | 17/01/2023 | 16/07/2023 | MODERN CONSTRUCTION | 45.93 | 39.48 | 85.97 | 60
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Repair And Renovation Works Of OHR (100 Cum) of Ground Water Based Supply Scheme for Hazi Mohammadpur Zone-II of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000280/2023-2024 | 997/BD-I | 30/10/2023 | 21/06/2025 | TANBEER CONSTRUCTION | 6.76 | 5 | 73.86 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Hazi Mohammadpur Zone - II to Accommodate FHTC. | SM/12590 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HAZI MOHAMMADPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000894/2021-2022 | 279/BD-I | 08/03/2022 | 18/03/2022 | ENVIROTECH SOLUTIONS | 2.46 | 2.45 | 99.31 | 1
Total | [13 empty] | 74.08 | 49.26 | 66.5