## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for DIAR SYAMPUR ZONE-I Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000879/2021-2022 | 263/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.37 | 2.35 | 99.17 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Augmentation of Diar Syampur Zone-I Piped water supply scheme to accommodate construction of OHR, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I |  | ORD/000148/2023-2024 | 671/BD-I | 09/08/2023 | 14/06/2024 | S.K. CONSTRUCTION DEBKUNDU , P.S.- BELDANGA, | 121.57 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Diar Shyampur Zone-I ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I |  | ORD/000104/2022-2023 | 1413/BD-I | 04/01/2023 | 14/01/2023 | MONDAL ENTERPRISE VILL-KALIKAHARA, P.O.-FARIDPUR | 2.36 | 1.52 | 64.46 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Replacement of sand layers,Activated Alumina & existing gravel for Modified Sujapur Sadipur Model after washing of AIRP allied (Capacity 11.00 Cum/hr) at Diar Syampur Zone-I Water Supply Scheme under Jal Jivan Mission of Bhagwangola-II Block under Berhampore Div-I,Murshidabad PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000018/2024-2025 | 926/BD-I | 07/06/2024 | 07/07/2024 | M/S GHOSH ENTERPRISE | 16.45 | 15.41 | 93.66 | 50
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Improvement Works for RCC Elevated Reservoir (45 Cum) of Diar Shyampur Zone-I piped water supply scheme under JJM within Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I | Junior Engineer-I | ORD/000148/2024-2025 | 1622/BD-I | 03/10/2024 | 08/01/2025 | M/S. SOUMITRA MONDAL | 3.4 | 3.38 | 99.52 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Diar Syampur Zone- I to Accommodate FHTC. | SM/12738 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000060/2023-2024 | 196/BD-I/7 | 09/02/2024 | 09/02/2024 | Resource Division | 10.99 | 0 | 0 | 0
Total | [13 empty] | 157.15 | 22.67 | 14.43