## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Faridpur ground water based water supply scheme under Block- Bhagawangola-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000058/2023-2024 | 4333/MEDB | 29/12/2023 | 29/03/2024 | ASSOCIATED ELECTRICAL CO. | 11.41 | 9.48 | 83.07 | 20
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000049/2023-2024 | 196/BD-I/16 | 09/02/2024 | 09/02/2024 | Resource Division | 38.7 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Faridpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I |  | ORD/000041/2023-2024 | 44/BD-I | 24/04/2023 | 24/05/2023 | SUJIT KUMAR SAHA | 8.99 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for FARIDPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000886/2021-2022 | 269/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.7 | 2.7 | 100 | 1
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Foridpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE | ORD/000114/2022-2023 | 1411/BD-I | 04/01/2023 | 14/01/2023 | S. K. ENTERPRISE, PROP-SANDIP GHOSH | 2.23 | 1.41 | 63.09 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Faridpur | SM/12739 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Faridpur water supply scheme of Bhagwangola-II block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000005/2024-2025 | 893/BD-I | 06/06/2024 | 06/07/2024 | SK CONSTRUCTION VILL-MAJDIA, P.O.-BERHAMPORE | 8.56 | 8.04 | 93.92 | 100
Total | [13 empty] | 72.59 | 21.62 | 29.78