## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SUNDARPUR Water Supply Scheme of BHAGAWANGOLA-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000881/2021-2022 | 265/BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.68 | 2.68 | 100 | 100
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Formal Work order for Augmentation of Sundarpur Piped water supply scheme to accommodate construction of OHR, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000161/2022-2023 | 1447/BD-I | 17/01/2023 | 15/03/2026 | M/S TAPAS KUMAR CHAKRABORTY | 397.04 | 131.89 | 33.22 | 85
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II under Sundarpur ground water based water supply scheme under Block_ Bhagwangola-I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000045/2023-2024 | 3735/MEDB | 03/11/2023 | 03/05/2024 | M/S JIT ENTERPRISE | 22.36 | 9.98 | 44.62 | 7
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Sundarpur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | Junior Engineer-I | ORD/000284/2022-2023 | 1807/BD-I | 31/03/2023 | 16/09/2025 | SUJIT KUMAR SAHA | 18.01 | 6.99 | 38.8 | 50
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Allied work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of OHR, pump house, boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission and Bhagwangola-I Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000206/2023-2024 | 859/BD-I | 07/09/2023 | 07/10/2023 | M/S TAPAS KUMAR CHAKRABORTY | 29.77 | 29.75 | 99.93 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Repair And Renovation Works Of R.C.C Elevated Reservoir (350 Cum) for Sundarpur water supply scheme of Bhagwangola-I block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | Junior Engineer-I | ORD/000303/2023-2024 | 1071/BD-I | 21/11/2023 | 21/12/2023 | HAFIZUL SK | 8.51 | 8.35 | 98.02 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Sundarpur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-I) | Assistant Engineer-I | Junior Engineer | ORD/000109/2022-2023 | 1439/BD-I | 16/01/2023 | 15/02/2023 | M/S RAMI CONSTRUCTION | 1.81 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Balance work for the work of Augmentation of Sundarpur Piped water supply scheme to accommodate construction of Pump House ,Boundary Wall, Service Road and laying of distribution of pipeline under Jal Jeevan Mission within Bhagwangola -I Block of Murshidabad District under Berhampore Division -I PHE. Dte. | Assistant Engineer-I | Junior Engineer-I | ORD/000126/2024-2025 | 1474/BD-I | 06/09/2024 | 05/11/2024 | M/S TAPAS KUMAR CHAKRABORTY | 89.63 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000067/2023-2024 | 196/BD-I/14 | 09/02/2024 | 09/02/2024 | Resource Division | 34.78 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | NEW CONNECTION AT SUNDARPUR PH-I |  |  | BILL/00244/2024-2025 | 110/WBSEDCL-JJM | 05/06/2024 | 05/06/2024 | WBSEDCL | 7.33 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sundarpur to Accommodate FHTC. | SM/12822 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Sundarpur ground water supply scheme in Bhagwabgola-I Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I |  | ORD/000089/2025-2026 | 949/BD-I | 18/07/2025 | 14/05/2026 | M/S S. DAS & ENTERPRISE | 122.8 | 0 | 0 | 0
Total | [13 empty] | 734.73 | 189.64 | 25.81