## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I of Jhikra ground water based water supply scheme under Block- Bhagwangola-II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001436/2023-2024 | 4320/MEDB | 29/12/2023 | 29/03/2024 | A.G. ENTERPRISE | 11.17 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000053/2023-2024 | 196/BD-I/5 | 09/02/2024 | 09/02/2024 | Resource Division | 5.7 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | JHIKRA PWSS |  |  | BILL/01453/2023-2024 | 347/WBSEDCL-JJM | 15/02/2024 | 15/02/2024 | WBSEDCL | 2.14 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Augmentation of JHIKRA Piped water supply scheme to accommodate construction of OHR ,pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000202/2022-2023 | 1615/BD-I | 02/03/2023 | 06/01/2024 | KAMIRUL SK AND CO. | 418.14 | 0 | 0 | 35
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for JHIKRA Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000888/2021-2022 | 271//BD-I | 08/03/2022 | 18/03/2022 | CIVIL & ENVIRONMENTAL ENGINEERING DESIGN SOLUTIONS | 2.75 | 0 | 0 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Jhikra ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Bhagwangola-II) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000112/2022-2023 | 1365/BD-I | 21/12/2022 | 20/01/2023 | AZAD ENTERPRISE | 2.41 | 0 | 0 | 100
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Jhikra Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000283/2022-2023 | 1806/BD-I | 31/03/2023 | 30/04/2023 | SUJIT KUMAR SAHA | 8.99 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forJhikra water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000260/2023-2024 | 1029/BD-I | 01/11/2023 | 01/12/2023 | MARUTI CONSTRUCTION & CO. | 7.67 | 0 | 0 | 100
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Jhikra. | SM/12823 | Augmentation | Allied work for the work of Augmentation of Jhikra Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Fanctional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block in Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000019/2024-2025 | 927/BD-I | 07/06/2024 | 07/07/2024 | KAMIRUL SK AND CO. | 28.79 | 0 | 0 | 100
Total | [13 empty] | 487.76 | 0 | 0