## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BENIPUR Water Supply Scheme of BHAGAWANGOLA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I |  | ORD/000174/2022-2023 | 1076/BD-I | 29/09/2022 | 09/10/2022 | NATSOL CONSULTANT | 2.92 | 2.92 | 100 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Formal work order for Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, toilet, pump house ,boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Bhagwangola-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000138/2022-2023 | 1448/BD-I | 17/01/2023 | 13/10/2025 | KAMIRUL SK AND CO. | 472.43 | 66.33 | 14.04 | 50
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I & II of BENIPUR ground water based water supply scheme under Block- Bhagawangola- II, Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000812/2023-2024 | 3765/MEDB | 03/11/2023 | 03/02/2024 | TARUN KUMAR BHATTACHARYA | 25.87 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Benipur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (2 nos Tubewell) | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000286/2022-2023 | 1810/BD-I | 31/03/2023 | 14/09/2025 | SUJIT KUMAR SAHA | 18.01 | 6.42 | 35.66 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Repair And Renovation Works Of RCC Elevated Reservoir (450 Cum) for Benipur water supply scheme of Bhagwangola-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000263/2023-2024 | 985/BD-I | 30/10/2023 | 22/01/2025 | SHIBAM ENTERPRISE | 8.54 | 8.39 | 98.25 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000001/2023-2024 | 61/BD-1/3 | 27/04/2023 | 27/04/2023 | Resource Division | 36.06 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Allied work for the work of Augmentation of Benipur Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Fanctional Household Tap Connection) under Jal Jeevan Mission in Bhagwangola-II Block in Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000020/2024-2025 | 928/BD-I | 07/06/2024 | 07/07/2024 | KAMIRUL SK AND CO. | 28.79 | 27.78 | 96.49 | 100
8 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | NEW CONNECTION AT BENIPUR PH-I |  |  | BILL/00469/2024-2025 | 147/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 11.24 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | NEW CONNECTION AT BENIPUR PH-I |  |  | BILL/00430/2024-2025 |  | 27/06/2024 | 27/06/2024 | WBSEDCL | 11.24 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Benipur ground water supply scheme in Bhagwabgola-II Block, Dist_Murshidabad under MEDB PHE Dte." | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000014/2025-2026 | 1139/MEDB | 13/05/2025 | 13/08/2025 | DIPALI CONSTRUCTION | 39.95 | 0 | 0 | 0
11 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Benipur Water Sub Mission Scheme to accommodate FHTC ( Functional House Hold Tap Connection ) in Bhagawangola - II Block of Murshidabad District under Berhampore Division -I , PHE Dte. | SM/12824 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Benipur ground water supply scheme in Bhagwabgola-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer-I |  | ORD/000367/2024-2025 | 327/BD-I | 25/02/2025 | 22/12/2025 | J.S. CONSTRUCTION | 122.8 | 0 | 0 | 0
Total | [13 empty] | 777.84 | 111.85 | 14.38