## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2023-2024 | 61/BD-1/9 | 27/04/2023 | 27/04/2023 | Resource Division | 57.59 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | RAMNAGAR DOEMKANUN ZONE-I PART-B PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000137/2024-2025 | 1552/BD-I | 24/09/2024 | 23/11/2024 | M/S B.M. INDUSTRIES | 20.64 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | NEW CONNECTION RAMNAGAR DEOMKANUN Z-1 PH-I |  |  | BILL/01631/2023-2024 | 470/WBSEDCL-JJM | 19/03/2024 | 19/03/2024 | WBSEDCL | 12.56 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | Augmentation of Ramnagar Doemkanun Zone-I(Part-B) Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000179/2023-2024 | 695/BD-I | 11/08/2023 | 29/04/2025 | M/S SINHA & SONS | 408.86 | 0 | 0 | 25
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | Construction of Service Road for approach and Pump House at Augmentation of Ramnagar Doemkanon Zone-I (Part-B) PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer |  | ORD/000054/2024-2025 | 1120/BD-I | 11/07/2024 | 09/09/2024 | S.K ENTERPRISE (RANITALA) | 7.92 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of Ramnagar Doemkanun Zone-I (Part-B) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000073/2025-2026 | 840/BD-I | 23/06/2025 | 22/08/2025 | PRADIP MAHATO | 19 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-B) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14044 | Augmentation | Continuation for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000302/2022-2023 | 1384/BD-I | 23/12/2022 | 02/01/2023 | RADIANT | 2.94 | 0 | 0 | 100
Total | [13 empty] | 529.5 | 0 | 0