## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-I Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000196/2022-2023 | 1379/BD-I | 22/12/2022 | 01/01/2023 | RADIANT | 2.94 | 2.85 | 96.89 | 100
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Augmentation of RamnagarDoemkanun Zone_I (Part-A)Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000243/2022-2023 | 1613/BD-I | 02/03/2023 | 14/02/2026 | SUJIT KUMAR SAHA | 249.53 | 195.75 | 78.45 | 85
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000037/2023-2024 | 61/BD-1/25 | 27/04/2023 | 27/04/2023 | Resource Division | 29.78 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Allied work for Laying of Distribution pipeline of Ramnagar Doemkanon Zone - I PWSS within Raninagar - II Block under JJM of Murshidabad district under Berhampore Division - I P.H.Engg Dte. | Assistant Engineer | Junior Engineer-II | ORD/000123/2024-2025 | 1471/BD-I | 06/09/2024 | 11/07/2026 | MAA CONSTRUCTION | 26.47 | 0 | 0 | 85
5 | MURSHIDABAD |  | Central Drilling | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 36.77 | 5.11 | 20
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Improvement of OHR (350 Cum) of Ground Water Based Supply Scheme for Augmentation of Ramnagar Domkanun Zone-I Part-A of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000003/2024-2025 | 891/BD-I | 06/06/2024 | 06/07/2024 | PRAVAT KUMAR GHOSH | 8.66 | 6.89 | 79.55 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Construction of Boundary Wall with Main Entrance gate and barbed wire facing and service road for approach at Augmentation of Ramnagar Doemkanun Zone-I (Part-A) PWSS of Raninagar-I Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000043/2024-2025 | 1066/BD-I | 03/07/2024 | 02/04/2025 | MUNNA AGROTECH ENTERPRISE | 20.5 | 11.29 | 55.09 | 55
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Construction Pump House Cum Chlorine Room at RAMNAGAR DOEMKANUN ZONE-I Water Supply Scheme under Jal Jevan Mission within Raninagar-II Block under Berhampore Division -I, PHE.Dte. In the district of Murshidabad. | Assistant Engineer |  | ORD/000326/2024-2025 | 273/BD-I | 11/02/2025 | 12/04/2025 | TAIMUR SK | 7.5 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-I (PART-A) PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14045 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 3rd Tube Well Site of Ramnagar Doemkanun Zone- I(Part-A) PWSS under Jal Jeevan Mission within Raninagar -II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000087/2025-2026 | 876/BD-I | 01/07/2025 | 30/08/2025 | BISWAS CONSTRUCTION | 18.97 | 0 | 0 | 0
Total | [13 empty] | 1084.58 | 253.56 | 23.38