## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2023-2024 | 194/BD-I/2 | 09/02/2024 | 09/02/2024 | Resource Division | 30.59 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | Augmentation | NEW CONNECTION AT RAMNAGAR DOEMKANUN Z2 PH 2 ID 304268982 |  |  | BILL/01115/2024-2025 |  | 25/11/2024 | 25/11/2024 | WBSEDCL | 10.13 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | Augmentation | Augmentation of Ramnagar Doemkanun ZoneII Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE Dte. | Assistant Engineer | Junior Engineer-II | ORD/000254/2022-2023 | 1660/BD-I | 13/03/2023 | 09/09/2023 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 186.74 | 0 | 0 | 30
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED RAMNAGAR DOEMKANUN ZONE-II PWSS RANINAGAR -II BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14046 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNAGAR DOEMKANON ZONE-II Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000197/2022-2023 | 1380/BD-I | 22/12/2022 | 01/01/2023 | RADIANT | 2.6 | 0 | 0 | 100
Total | [13 empty] | 230.06 | 0 | 0