## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000006/2023-2024 | 61/BD-1/7 | 27/04/2023 | 27/04/2023 | Resource Division | 19.67 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II ,Zone-II under Hurshi ground water based water supply scheme under Block_ Raninagar_I Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000672/2023-2024 | 4296/MEDB | 29/12/2023 | 29/03/2024 | MONI ELECTRICAL WORKS | 20.92 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | shifting ltoh hurshi z2 ph 1 |  |  | BILL/01598/2023-2024 | 431/WBSEDCL-JJM | 12/03/2024 | 12/03/2024 | WBSEDCL | 0.34 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | Augmentation of Hurshi Zone-II Piped water supply scheme to accommodate construction of OHR, pump house and boundary wall , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000136/2023-2024 | 615/BD-I | 02/08/2023 | 30/09/2025 | ROY AND ROY CONSTRUCTION | 246.81 | 0 | 0 | 30
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Hurshi Zone-II Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. (For 2 nos. Tubewell) | Assistant Engineer |  | ORD/000314/2023-2024 | 1148/BD-I | 04/12/2023 | 03/01/2024 | NADIA TUBEWELLS | 23.12 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF GROUND WATER BASED HURSHI ZONE -II PWSS RANINAGAR -I BLOCK WITHIN MURSHIDABAD DISTRICT UNDER BERHAMPORE DIVISION -I , PHE DTE. | SM/14048 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for HURSHI ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000195/2022-2023 | 1330/BD-I | 16/12/2022 | 26/12/2022 | RADIANT | 2.53 | 0 | 0 | 100
Total | [13 empty] | 313.39 | 0 | 0