## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000009/2023-2024 | 61/BD-1/8 | 27/04/2023 | 27/04/2023 | Resource Division | 29.2 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | NEW SERVICE CONNECTION AT KOMNAGAR PH 1 ID 304268985 |  |  | BILL/01130/2024-2025 |  | 26/11/2024 | 26/11/2024 | WBSEDCL | 3.49 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Providing and installation of Electro_Mechanical equipment and Allied works for Arsenic Iron Removal Plant at Komnagar ground water supply scheme in Raninagar-II Block Dist_Murshidabad under MEDB PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000009/2025-2026 | 1133/MEDB | 13/05/2025 | 13/08/2025 | M/S K.P. PRAMANIK | 39.98 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Augmentation of Komnagar Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000122/2023-2024 | 506/BD-I | 24/07/2023 | 01/05/2025 | PRATICHI ENTERPRISE | 194.85 | 130.92 | 67.19 | 83
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Planning, Design, Investigation, Construction, Erection, Installation, Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code manual on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) ALONG WITH 3 (Three) years operation & Maintenance after succesful completion of 3 (Three) months Trial Run of "Augmentation of Komnagar ground water supply scheme in Raninagar-II Block, under Berhampore Division-I, P.H.E. Dte. (Capacity-30.00 Cum/Hr.) | Assistant Engineer |  | ORD/000288/2024-2025 | 56/BD-I | 14/01/2025 | 10/11/2025 | SUMAN ENTERPRISE AND SUMAN AQUA | 122.79 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Construction of Boundary Wall With Main Entrance gate and barbed wire facing ,Service Road for approach and Pump House at Augmentation of Komnagar PWSS of Raninagar-II Block under Jal Jeevan Mission of Murshidabad District under Berhampore Division-I, PHE Dte. (2nd Site)/New OHR Site | Assistant Engineer | Junior Engineer-II | ORD/000053/2024-2025 | 1119/BD-I | 11/07/2024 | 11/06/2025 | MODERN CONSTRUCTION (DOMKAL) | 25.76 | 0 | 0 | 75
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KOMNAGAR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000279/2022-2023 | 1763/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.53 | 2.49 | 98.5 | 100
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Improvement of OHR (90.8 Cum) of Ground Water Based Supply Scheme for Augmentation of Komnagar of Raninagar-I block under JJM under Berhampore Division-I PHE Dte. in the district Murshidabad. | Assistant Engineer | Junior Engineer-II | ORD/000052/2024-2025 | 1118/BD-I | 11/07/2024 | 07/01/2025 | M/S S.R.K ENTERPRISE | 6.48 | 4.88 | 75.25 | 100
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | Renovation for Filter media of Existing AIRP of (Capacity 18 Cum/hr.) at Komnagar Water Supply Scheme under Jal Jeevan Mission of Berhampore Division-I, PHEengineering Dte. | Assistant Engineer | Junior Engineer-II | ORD/000441/2023-2024 | 412/BD-I | 13/03/2024 | 12/04/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 13.04 | 12.95 | 99.32 | 100
10 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Komnagar . | SM/14049 | Augmentation | KOMNAGAR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of RANINAGAR-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000058/2024-2025 | 1130/BD-I | 11/07/2024 | 11/03/2025 | TAIMUR SK | 19.33 | 0 | 0 | 100
Total | [13 empty] | 457.46 | 151.25 | 33.06