## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000012/2023-2024 | 61/BD-1/1 | 27/04/2023 | 27/04/2023 | Resource Division | 13.4 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Repair And Renovation Works Of OHR (35 Cum) of Ground Water Based Supply Scheme for Ramchandrapur of Raninagar-II block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | Junior Engineer-II | ORD/000301/2023-2024 | 1069/BD-I | 21/11/2023 | 21/12/2023 | MADAN MOHAN SASMAL | 5.13 | 0 | 0 | 70
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Augmentation of Ramchandrapur Piped water supply scheme for laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | Junior Engineer-II | ORD/000246/2022-2023 | 1651/BD-I | 13/03/2023 | 09/09/2023 | MS BAPPA ENTERPRISE | 49.53 | 0 | 0 | 71
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at RAMCHANDRAPUR Water Supply Scheme (1st TW site) within RANINAGAR-II Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000330/2024-2025 | 280/BD-I | 12/02/2025 | 27/02/2025 | HAFIZUL SEIKH | 11.56 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMCHANDRAPUR Water Supply Scheme of RANINAGAR-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000278/2022-2023 | 1391/BD-I | 27/12/2022 | 06/01/2023 | M/S SOBHA & CO | 2.46 | 0 | 0 | 100
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Ramchandrapur . | SM/14050 | Augmentation | Renovation for Existing AIRP of (Capacity 6.57 Cum/hr.) at Ramchandrapur Water Supply Scheme under Jal Jeevan Mission of Berhampore Division-I, PHE Engineering Dte. | Assistant Engineer | Junior Engineer-II | ORD/000440/2023-2024 | 411/BD-I | 13/03/2024 | 12/04/2024 | SUMAN ENTERPRISE AND SUMAN AQUA | 9.15 | 0 | 0 | 80
Total | [13 empty] | 91.23 | 0 | 0