## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000015/2023-2024 | 194/BD-I/9 | 09/02/2024 | 09/02/2024 | Resource Division | 14.79 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Augmentation of Sarkarpara Piped water supply scheme to accommodate construction of boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Jalangi Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000224/2022-2023 | 1557/BD-I | 20/02/2023 | 16/06/2026 | AZAD ENTERPRISE | 63.96 | 0 | 0 | 75
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Sinking of 300mm x 200 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at SARKARPARA Water Supply Scheme within Jalangi Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer | JE_Pravin Kumar Gupta | ORD/000375/2024-2025 | 430/BD-I | 19/03/2025 | 03/04/2025 | TAPESH MONDAL | 11.56 | 0 | 0 | 100
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SARKARPARA Water Supply Scheme of JALANGI Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000282/2022-2023 | 1370/BD-I | 21/12/2022 | 31/12/2022 | M/S SOBHA & CO | 2.46 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Sarkarpara . | SM/14051 | Augmentation | Repair And Renovation Works Of OHR (45 Cum) of Ground Water Based Supply Scheme for Sarkarpara of Jalangi block under Berhampore Division-I PHEDte. in the district Murshidabad. Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000249/2023-2024 | 1092/BD-I | 24/11/2023 | 17/03/2025 | PARUL ELECTRICAL INSTALLER | 5.41 | 0 | 0 | 100
Total | [13 empty] | 98.18 | 0 | 0