## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Augmentation of Bajipur Madhupur Zone-II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte.(PART-A) | Assistant Engineer,Assistant Engineer-I | Junior Engineer | ORD/000181/2023-2024 | 697/BD-I | 11/08/2023 | 16/06/2024 | UNIVERSE UNEMPLOYED ENGINEERS CONSTRUCTION CO. | 335.43 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000076/2023-2024 | 201/BD-1/17 | 10/02/2024 | 10/02/2024 | Resource Division | 280.69 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000014/2024-2025 | 1510/BD-I/8 | 12/09/2024 | 12/09/2024 | Resource Division | 9.8 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for AUGMENTATION OF BAJUPUR MADHUPUR ZONE-II PIPED WATER SUPPLY SCHEME Block - Lalgola under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000540/2024-2025 | 326/MEDB | 10/02/2025 | 10/05/2025 | KARTICK BAL | 25.03 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BAJIPUR MADHUPUR ZONE-II Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000205/2022-2023 | 1383/BD-I | 23/12/2022 | 02/01/2023 | ENVIROTECH SOLUTIONS | 2.87 | 0 | 0 | 1
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF BAJUPUR MADHUPURZONE-II PIPED WATER SUPPLY SCHEME | SM/14067 | Augmentation | Repair And Renovation Works Of OHR (450 Cum) for Bajupur Madhupur Zone-II water supply scheme of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. Augmentation of PWSS under Jal Jeevan Mission. | Assistant Engineer | JE | ORD/000359/2023-2024 | 15/BD-I | 04/01/2024 | 29/11/2024 | MAA SANKARI ENTERPRISE | 8.61 | 0 | 0 | 100
Total | [13 empty] | 662.42 | 0 | 0