## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000192/2022-2023 | 1320/BD-I | 13/12/2022 | 23/12/2022 | TECHVISION | 2.81 | 2.81 | 99.98 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III , Zone-I under RAMNACHANDPUR ground water based water supply scheme under Block_ Nowda Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I | Junior engineer-II | ORD/000069/2023-2024 | 1883/MEDB | 16/06/2023 | 16/09/2023 | CONCORD ENGINEERING | 35.22 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Continuation work order for Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAMNACHANDPUR ZONE-I Water Supply Scheme of NOWDA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_RAJIB BISWAS | ORD/000004/2023-2024 | 40/BD-I | 20/04/2023 | 30/04/2023 | TECHVISION | 2.81 | 2.81 | 100 | 100
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000056/2023-2024 | 196/BD-I/18 | 09/02/2024 | 09/02/2024 | Resource Division | 7.99 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of Ramnachandpur Zone-I" ground water supply scheme in NAWDA Block, under Berhampore Division-I, P.H.E Dte(Capacity-98.00 Cum/hr.) Type-1: Fully Gravity System with RG Filter | Assistant Engineer-II |  | ORD/000038/2024-2025 | 1037/BD-I | 28/06/2024 | 28/06/2025 | ACQUA CONSTRUCTION CONSORTIUM | 234.01 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF RAMNACHANDPUR ZONE-I PIPED WATER SUPPLY SCHEME. | SM/14068 | Augmentation | Augmentation of Ramnachandpur Zone_I Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Nawda Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE | ORD/000250/2022-2023 | 1655/BD-I | 13/03/2023 | 03/04/2025 | SOFIQUL ISLAM | 371.52 | 316.8 | 85.27 | 95
Total | [13 empty] | 654.35 | 322.41 | 49.27