## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Augmentation of Nasipur zone_II Piped water supply scheme to accommodate construction of OHR , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,Assistant Engineer-I | JE | ORD/000140/2023-2024 | 625/BD-I | 03/08/2023 | 01/10/2025 | M/S BIMALENDU BOSE | 374.96 | 194.24 | 51.8 | 10
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for NASIPUR ZONE-I Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000007/2023-2024 | 48/BD-I | 25/04/2023 | 05/05/2023 | ENVIROTECH SOLUTIONS | 2.45 | 2.45 | 100 | 100
3 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | NASIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE | ORD/000451/2023-2024 | 454/BD-I | 15/03/2024 | 14/05/2024 | INDRAJIT DUBEY | 22.41 | 14.28 | 63.71 | 50
4 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 7.05 | 0.98 | 20
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000075/2023-2024 | 201/BD-1/16 | 10/02/2024 | 10/02/2024 | Resource Division | 303.88 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000017/2024-2025 | 1510/BD-I/11 | 12/09/2024 | 12/09/2024 | Resource Division | 5.48 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at NASIPUR ZONE-II Water Supply Scheme(2nd TW Site) within Lalgola Block under JJM in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte. | Assistant Engineer |  | ORD/000364/2024-2025 | 319/BD-I | 24/02/2025 | 11/03/2025 | MAMATA USHA ENTERPRISE | 9.01 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Construction of Pump House Cum Chlorine Room with boundary wall at 2nd Tube Well Site of NASIPUR ZONE - II PWSS under Jal Jeevan Mission within Lalgola Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer |  | ORD/000376/2024-2025 | 431/BD-I | 19/03/2025 | 18/05/2025 | ABA CONTRACTOR | 18.98 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Nasipur Zone-II. | SM/14069 | Augmentation | Construction Pump House Cum Chlorine Room at Head Work site of Nasipur Zone -II Water Supply Scheme under Jal Jevan Mission of Lalgola Block of Murshidabad District under Berhampore Division -I, PHE.Dte. | Assistant Engineer | JE | ORD/000069/2025-2026 | 823/BD-I | 18/06/2025 | 02/08/2025 | M/S B. P. ENTERPRISE | 8.47 | 0 | 0 | 50
Total | [13 empty] | 1465.87 | 218.02 | 14.87