## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for KASHIPUR ZONE-II Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000232/2022-2023 | 1590/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.6 | 2.6 | 99.99 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000091/2023-2024 | 196/BD-I/25 | 09/02/2024 | 09/02/2024 | Resource Division | 48.51 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Planning,Design,Investigation,Construction,Erection,Installation,Completion testing and Commissioning in all respect of entire units of Arsenic cum Iron Removal Plant (AIRP) of different capacities capable of removing arsenic & Iron Present in Ground Water in different concentration to acceptable limit as per latest BIS Code on basis of departmental process drawing (MODIFIED SUJAPUR SADIPUR) along with 5 (Five) years Operation & Maintenance after successful completion of 3 (three) months Trial Run of "Augmentation of KASHIPUR ZONE-II" ground water supply scheme in BELDANGA-II Block, under Berhampore Division-I, P.H.E Dte(Capacity-48.00 Cum/hr.) Type-4: Partial Gravity System with Pressure Filter and Pressurized Up flow Polishing | Assistant Engineer-II | JE | ORD/000039/2024-2025 | 1038/BD-I | 28/06/2024 | 28/06/2025 | EFFLUENT & WATER TREATMENT ENGINEERS (P) LTD | 156.07 | 0 | 0 | 60
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | KASHIPUR ZONE-II PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000051/2024-2025 | 1117/BD-I | 11/07/2024 | 07/01/2025 | HI-TECH ENGINEERS CO-OPERATIVE & CONSTRUCTION SOCIETY LTD. | 20.67 | 0 | 0 | 100
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Allied Work for Road Restoration, Laying of Balance portion of UPVC and Rising Mains at Kashipur Zone-II PWSS under Jal Jeevan Mission within Beldanga-II block under Berhampore Division-I, P.H.E. Dte. In the district of Murshidabad. | Assistant Engineer-II |  | ORD/000064/2025-2026 | 777/BD-I | 22/05/2025 | 20/08/2025 | MARUTI CONSTRUCTION & CO. | 64.87 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of KASHIPUR ZONE - II PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000038/2025-2026 | 667/BD-I | 29/04/2025 | 21/10/2025 | DEBEN RAJAK | 10.18 | 0 | 0 | 100
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Augmentation of Kashipur zone_II Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE Dte. | Assistant Engineer-II | JE,Junior Engineer-I | ORD/000242/2022-2023 | 1599/BD-I | 28/02/2023 | 16/08/2025 | MARUTI CONSTRUCTION & CO. | 150.14 | 122.97 | 81.9 | 95
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF KASHIPUR (ZONE II) PIPED WATER SUPPLY SCHEME. | SM/14427 | Augmentation | Repair And Renovation Works Of OHR (550 Cum) for Kasipur Zone-II water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-II | Junior Engineer-I | ORD/000270/2023-2024 | 991/BD-I | 30/10/2023 | 25/10/2024 | PRAVAT KUMAR GHOSH | 9.15 | 7.73 | 84.45 | 100
Total | [13 empty] | 462.19 | 133.3 | 28.84