## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for SITESNAGAR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000259/2022-2023 | 1682/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.53 | 2.53 | 100.3 | 1
2 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Augmentation of Sitesnagar Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer | JE | ORD/000222/2022-2023 | 1542/BD-I | 17/02/2023 | 01/11/2025 | M/S JOGMAYA ENTERPRISE | 87.18 | 54.67 | 62.71 | 30
3 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Repair And Renovation Works Of OHR (204 Cum) of Ground Water Based Supply Scheme for Sitesnagar of Lalgola block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer | JE | ORD/000281/2023-2024 | 998/BD-I | 30/10/2023 | 19/03/2025 | M/S SAJAL KUMAR NATH AND CO. | 7.99 | 0 | 0 | 100
4 | MURSHIDABAD |  | Central Drilling | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Construction of Big Diameter Tube-Well by Deploying of Suitable Capacity Drilling Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different Districts for Different Water Supply Schemes Including Procurement & Installation Pumping Machinery with All Allied Accessories at the Above Constructed Tube-Wells Under JJM Program throughout the State of West Bengal. (2ed call of NIET 25 of 2022-23) |  |  | ORD/000215/2023-2024 | 2235/CDD | 11/03/2024 | 11/08/2024 | JHARGRAM SPV PRIVATE LIMITED | 720.23 | 0 | 0 | 20
5 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000077/2023-2024 | 201/BD-1/18 | 10/02/2024 | 10/02/2024 | Resource Division | 16.95 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000016/2024-2025 | 1510/BD-I/10 | 12/09/2024 | 12/09/2024 | Resource Division | 2.19 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR SITESHNAGAR ,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14428 | Augmentation | Balance and allied Work Laying Rising Main with DI (K-9) and distribution system with UPVC pipe including supply of necessary special for augmentation work of Siteshnagar Water Supply Scheme , under Jal Jevan Mission under Berhampore Division -I , PHE.Dte. of LALGOLA Block of Murshidabad District. | Assistant Engineer | JE | ORD/000281/2024-2025 | 09/BD-I | 06/01/2025 | 04/07/2025 | M/S. JOGMAYA ENTERPRISE | 23.22 | 0 | 0 | 30
Total | [13 empty] | 860.29 | 57.21 | 6.65