## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augmentation in connection to Accommodate FHTC at Pump House No.-I ,Zone-II of Bishnupur ground water based water supply scheme under Block- RANINAGAR-I Dist. Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/001435/2023-2024 | 4316/MEDB | 29/12/2023 | 29/03/2024 | S.P. ENTERPRISE (BAGUIHATI) | 10.62 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000021/2023-2024 | 194/BD-I/6 | 09/02/2024 | 09/02/2024 | Resource Division | 42.69 | 0 | 0 | 0
3 | MURSHIDABAD |  | Central Drilling | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | Augmentation | Construction of Big diameter Tube-Well by Deployment of Suitable capacity Rig (Direct Rotary, Reverse Rotary, Odex Method) at Different District for Different Water Supply Schemes Including Procurement & Installation Pumping machinery with All Allied accessories at the Above Constructed Tube - Wells under JJM Program throughout the State of West Bengal. (2nd call of NIET 25 of 2022-23). | Assistant Engineer,Driller In Charge | Junior Engineer | ORD/000022/2024-2025 | 492/CDD | 23/07/2024 | 23/10/2024 | JHARGRAM SPV PRIVATE LIMITED | 458.7 | 6.61 | 1.44 | 10
4 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | Augmentation | Formal work order for Augmentation of Bishnupur Zone-II Piped water supply scheme to accommodate construction of Pump house, boundary wall and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Raninagar-I Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | JE_Pravin Kumar Gupta,Junior Engineer-I | ORD/000178/2022-2023 | 1541/BD-I | 16/02/2023 | 29/08/2025 | NATIONAL CONSTRUCTION | 190.09 | 181.89 | 95.69 | 95
5 | MURSHIDABAD |  | Berhampore Division I | Augmentation of Ground Water Based Piped Water Supply Scheme for Bishnupur Zone- II . | SM/14429 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for BISHNUPUR ZONE-II Water Supply Scheme of RANINAGAR-I Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte | Assistant Engineer-I | JE_Pravin Kumar Gupta | ORD/000270/2022-2023 | 1761/BD-I | 24/03/2023 | 03/04/2023 | M/S SOBHA & CO | 2.6 | 2.6 | 100 | 100
Total | [13 empty] | 704.7 | 191.1 | 27.12