## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for CHARKAMNAGAR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000234/2022-2023 | 1592/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.74 | 2.74 | 100 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKAMNAGAR ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. |  |  | ORD/000061/2023-2024 | 3778/MEDB | 26/05/2023 | 26/08/2023 | WEST BENGAL ENGINEERING CO. | 35.2 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 196/BD-I/20 | 09/02/2024 | 09/02/2024 | Resource Division | 77.09 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Augmentation of Charkamnagar Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000157/2023-2024 | 681/BD-I | 10/08/2023 | 26/04/2026 | MERCURY ENGINEERING COMPANY | 418.24 | 0 | 0 | 7
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Allied work for Laying of distribution pipeline of CHARKAMNAGAR and allied works within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000179/2024-2025 | 2122/BD-I | 27/11/2024 | 11/01/2025 | NOVELTY CONSTRUCTION | 46.47 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of CHARKAMNAGAR Ground Piped Water Supply Scheme under Jal Jeevan Mission within Beldanga - II Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000332/2024-2025 | 279/BD-I | 12/02/2025 | 14/03/2025 | MERCURY ENGINEERING COMPANY | 25.63 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of CHARKAMNAGAR ZONE-I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000039/2025-2026 | 672/BD-I | 29/04/2025 | 13/06/2025 | JAMUNA CONSTRUCTION | 10.18 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) forCharkamnagar water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-II | JE | ORD/000252/2023-2024 | 1011/BD-I | 31/10/2023 | 23/01/2025 | PARTHA PRATIM DAS | 8.36 | 0 | 0 | 100
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Charkamnagar Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer-II | JE | ORD/000391/2023-2024 | 155/BD-I | 05/02/2024 | 06/03/2024 | NADIA TUBEWELLS | 18.01 | 14.57 | 80.89 | 100
Total | [13 empty] | 641.93 | 17.3 | 2.7