## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for CHARKAMNAGAR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000234/2022-2023 | 1592/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.74 | 2.74 | 100 | 0
2 | MURSHIDABAD |  | Berhampore Mechanical | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I ,II & III under CHARKAMNAGAR ground water based water supply scheme under Block_ Beldanga-II Dist. - Murshidabad under MEDB, PHE Dte. |  |  | ORD/000061/2023-2024 | 3778/MEDB | 26/05/2023 | 26/08/2023 | WEST BENGAL ENGINEERING CO. | 35.2 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000084/2023-2024 | 196/BD-I/20 | 09/02/2024 | 09/02/2024 | Resource Division | 77.09 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Augmentation of Charkamnagar Piped water supply scheme to accommodate construction of OHR, Pump House, Boundary wall and service road, laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000157/2023-2024 | 681/BD-I | 10/08/2023 | 26/04/2026 | MERCURY ENGINEERING COMPANY | 418.24 | 0 | 0 | 7
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 87 Cum/hr.) with allied work at Charkamnagar Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II |  | ORD/000010/2024-2025 | 905/BD-I | 07/06/2024 | 07/07/2024 | M/S S.S ENTERPRISE VILL. & P.O.-BHAGIRATHPUR | 29.25 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Allied work for Laying of distribution pipeline of CHARKAMNAGAR and allied works within Beldanga-II Block under Berhampore Division-I, PHE Dte. in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000179/2024-2025 | 2122/BD-I | 27/11/2024 | 11/01/2025 | NOVELTY CONSTRUCTION | 46.47 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Bored Cast-in-situ_ M30 _ grade 500 mm dia. R.C.C. pile for Construction of OHR at Head Work site of CHARKAMNAGAR Ground Piped Water Supply Scheme under Jal Jeevan Mission within Beldanga - II Block under Berhampore Division-I, PHE.Dte. in the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000332/2024-2025 | 279/BD-I | 12/02/2025 | 14/03/2025 | MERCURY ENGINEERING COMPANY | 25.63 | 0 | 0 | 0
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF CHARKAMNAGAR PIPED WATER SUPPLY SCHEME. | SM/14430 | Augmentation | Construction of Boundary wall at 2nd Tube Well Site of CHARKAMNAGAR ZONE-I PWSS under Jal Jeevan Mission within Beldanga-II Block under Berhampore Division -I, PHE.Dte.in the district of Murshidabad. | Assistant Engineer-II |  | ORD/000039/2025-2026 | 672/BD-I | 29/04/2025 | 13/06/2025 | JAMUNA CONSTRUCTION | 10.18 | 0 | 0 | 0
Total | [13 empty] | 644.81 | 2.74 | 0.42