## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for MASHIMPUR Water Supply Scheme of BELDANGA-II Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-II |  | ORD/000233/2022-2023 | 1591/BD-I | 28/02/2023 | 10/03/2023 | TECHVISION | 2.6 | 2.6 | 100 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Proposed balance work for office room at 1st floor over AIRP pump house with staircase at Mashimpur ground water supply scheme under JJM under Berhampore Division-I, P.H.E Dte. | Assistant Engineer-II | Junior Engineer-I | ORD/000442/2023-2024 | 441/BD-I | 15/03/2024 | 14/04/2024 | CLASSIC CONSTRUCTION | 2.61 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000088/2023-2024 | 196/BD-I/22 | 09/02/2024 | 09/02/2024 | Resource Division | 14.87 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Augmentation of Mashimpur Piped water supply scheme to accommodate construction of service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Beldanga-II Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer-II | JE | ORD/000029/2023-2024 | 81/BD-I | 28/04/2023 | 25/10/2023 | SUJIT KUMAR SAHA | 241.41 | 73.06 | 30.26 | 40
5 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Allied works of Laying of distribution pipeline of MASHIMPUR piped water supply scheme under JJM within Beldanga-II Block in the district of Murshidabad under Berhampore Division-I, PHE Dte. | Assistant Engineer-II |  | ORD/000128/2024-2025 | 1478/BD-I | 06/09/2024 | 06/10/2024 | SANTANU BISWAS | 16.93 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Improvement of Existing AIRP of (Capacity 51 Cum/hr.) with allied works at Mashimpur Water Supply Scheme under Jal Jeevan Mission within Beldanga - II under Berhampore Division-I, P.H.Eengineering Dte. In the district of Murshidabad. | Assistant Engineer-II | JE | ORD/000079/2025-2026 | 846/BD-I | 23/06/2025 | 23/07/2025 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 6.4 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Repair And Renovation Works Of OHR (250 Cum) forMashimpur water supply scheme of Beldanga-II block under Berhampore Division-I PHE Dte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer-II | Junior Engineer-I | ORD/000254/2023-2024 | 1015/BD-I | 31/10/2023 | 30/11/2023 | SOUMEN ADHIKARY | 7.83 | 7.29 | 93.08 | 100
8 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | MASHIMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of BELDANGA-II Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer-II | JE | ORD/000457/2023-2024 | 461/BD-I | 15/03/2024 | 09/01/2025 | JALALUDDIN SHAH | 21.7 | 5.38 | 24.79 | 100
9 | MURSHIDABAD |  | Berhampore Division I | AUGMENTATION OF MASHIMPUR PIPED WATER SUPPLY SCHEME. | SM/14431 | Augmentation | Replacement of Filter media of Existing AIRP of (Capacity 51 Cum/hr.) with allied work at Mashimpur Water Supply Scheme under Jal Jeevan Mission under Berhampore Division-I, PHEengineering Dte. | Assistant Engineer-II | JE | ORD/000011/2024-2025 | 910/BD-I | 07/06/2024 | 05/10/2024 | M/S S.S ENTERPRISE ABDUS SAMAD ROAD | 17.45 | 14.85 | 85.09 | 100
Total | [13 empty] | 331.79 | 103.18 | 31.1