## Work Order tracking
Work Order tracking (Rs. in Lakh)
Sl No. | District | Block | Division | Scheme | Sm Code | Scheme Category | Work Name | Name of AE entrusted | Name of JE entrusted | System Order No. | WO Number | WO Date | WO End Date | Agency Name | Work Value | Payment | Payment % | Physical Progress %
1 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Providing, installation and commissioning of submersible pumping machinery along with allied Electro-Mechanical works for Augumentation in connection to Accommodate FHTC at Pump House No.-I & II under RAJARAMPUR ground water based water supply scheme under Block_ Lalgola Dist. - Murshidabad under MEDB, PHE Dte. | ASSISTANT ENGINEER-I,ASSISTANT ENGINEER-II | Junior engineer-I,Junior engineer-II,Junior engineer-III | ORD/000068/2023-2024 | 3781/MEDB | 03/11/2023 | 03/02/2024 | M/S S. R. ENTERPRISE | 23.47 | 0 | 0 | 0
2 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | RAJARAMPUR PWSS to accommodate construction of Boundary Wall under Jal Jivan Mission of LALGOLA Block, Murshidabad District under Berhampore Division-I, PHE.Dte. | Assistant Engineer | Junior Engineer | ORD/000454/2023-2024 | 457/BD-I | 15/03/2024 | 14/05/2024 | MAA DURGA ENTERPRISE | 22.87 | 0 | 0 | 0
3 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000080/2023-2024 | 201/BD-1/21 | 10/02/2024 | 10/02/2024 | Resource Division | 50.95 | 0 | 0 | 0
4 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Material Requisition To Resource Division |  |  | RTOR000010/2024-2025 | 1510/BD-I/4 | 12/09/2024 | 12/09/2024 | Resource Division | 8.03 | 0 | 0 | 0
5 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I |  |  | BILL/00429/2024-2025 |  | 27/06/2024 | 27/06/2024 | WBSEDCL | 0.89 | 0 | 0 | 0
6 | MURSHIDABAD |  | Berhampore Mechanical | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | SHIFTING OF LT OH LINE AT RAJARAMPUR PH-I |  |  | BILL/00468/2024-2025 | 145/WBSEDCL-JJM | 08/07/2024 | 08/07/2024 | WBSEDCL | 0.89 | 0 | 0 | 0
7 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Repair and renovation of existing Pump House (Head work/2nd site) and Allied Works for Rajarampur ground Water Supply Scheme" under Berhampore Division-I, PHE Dte. (Block-Lalgola) | Assistant Engineer,Assistant Engineer-I | JE_RAJIB BISWAS,Junior Engineer | ORD/000121/2022-2023 | 1678/BD-I | 14/03/2023 | 13/04/2023 | SOMNATH DEY | 2.35 | 0 | 0 | 100
8 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Augmentation of Rajarampur Piped water supply scheme to accommodate construction of OHR ,Pump House and service road , laying of design pipeline and providing FHTC (Functional Household Tap Connection ) under Jal Jeevan Mission in Lalgola Block of Murshidabad District under Berhampore Division-I,PHE.Dte. | Assistant Engineer,Assistant Engineer-I | Junior Engineer,Junior Engineer-I | ORD/000208/2022-2023 | 1618/BD-I | 02/03/2023 | 06/01/2024 | DHIRENDRA NATH MONDAL | 366.26 | 0 | 0 | 0
9 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Repair And Renovation Works Of OHR (350 Cum) of Ground Water Supply Scheme for Rajarampur of Lalgola block under Berhampore Division-I PHEDte. in the district Murshidabad. For Augmentation of PWSS under Jal jeevan Mission. | Assistant Engineer,Assistant Engineer-I | JE,Junior Engineer | ORD/000277/2023-2024 | 994/BD-I | 30/10/2023 | 30/07/2025 | DAS CONSTRUCTION 13/1/2 UKILABAD ROAD, BERHAMPORE | 8.12 | 0 | 0 | 0
10 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Route Survey ,Design of distribution network and Preparation of DPR for providing FHTC (Functional House Hold Tap Connection) by Augmentation under Jal Swapna for RAJARAMPUR Water Supply Scheme of LALGOLA Block of Murshidabad District under Berhampore Division-I ,P.H.E Dte. | Assistant Engineer-I | JE | ORD/000261/2022-2023 | 1684/BD-I | 14/03/2023 | 24/03/2023 | ENVIROTECH SOLUTIONS | 2.66 | 0 | 0 | 1
11 | MURSHIDABAD |  | Berhampore Division I | AUGUMENTATION OF GROUND WATER BASED PIPED WATER SUPPLY SCHEME FOR RAJARAMPUR,BLOCK - LALGOLA , DISTRICT- MURSHIDABAD. | SM/14432 | Augmentation | Sinking of 250mm x 150 mm dia tube well 120.00 mtr. deep by direct rotary rig method using UPVC Pipe and UPVC Deep Well Screen (RDS) filter at Rajarampur Water Supply Scheme in connection with Augmentation work under Berhampore Division - I, P.H.Engineering Dte ( For 2 nos Tubewell) | Assistant Engineer,Assistant Engineer-I | JE | ORD/000037/2023-2024 | 139/BD-I | 12/05/2023 | 11/06/2023 | HARUN ALL RASHID & BROTHERS | 17.82 | 0 | 0 | 100
Total | [13 empty] | 504.3 | 0 | 0